## Read Me
IDEA Brand Coach — MCP Tool-Surface Improvement Plan
Prioritized by customer need · Alpha / Beta / Roadmap · 2026-06-25
Purpose | A priority-ordered backlog of improvements to the MCP / Claude-connector tool surface that supports the Alpha conversion-fix loop, the Beta retention loop, and as much of the roadmap as possible — ordered by our best understanding of actual customer need, pressure-tested against what was merely planned, and held to Trevor's guidance.
The product loop | Diagnose -> Analyse -> Fix -> Re-measure -> Defend (fixing low Amazon conversion). Free Trust Gap(TM) self-report -> paid forensic (review corpus -> Avatar 2.0(TM) -> the ONE Decision Trigger(TM)) -> design brief -> re-measure the lift -> Brand Defence (watch competitors = the subscription reason).
Two customers | P1 'Maya' (busy owner — compress, do-it-for-her, one next action). P2 'Rico' (operational VA — teach, scaffold, checklists). Same journey must adapt: compress vs scaffold, same substance.
How built | Multi-agent workflow: read the 20-skill architecture + strategy + tool surface + ICP journeys + roadmap; derived customer needs per loop-stage x ICP; adversarially challenged planned-vs-needed against Trevor's guidance; prioritized + reconciled.
Governing principles (Trevor)
• CONVERSION FIXER, never brand-strategy: every tool's user-facing prose must open on a number the seller owns and frame outputs as 'why your buyer isn't deciding and what to fix.' The moment a tool sounds like a brand questionnaire (onboard_choose's literal 'Simple Diagnostic vs Full Contextual Upload') or hands a free 'Signature', it loses differentiation. Reframe or cut on sight.
• P1 (Maya) first, then P2 (Rico), same substance, different delivery: Alpha excellence = answer-first, ends-on-ONE-action, NEVER homework for Maya; scaffolded/taught/reusable-checklist for Rico. The generate_brief no_canvas wall is the single worst P1 violation and is rank 1.
• Customer-need order beats surface-reach: prioritise the SPA path real testers hit THIS week over Trevor's N-of-1 MCP connector. Any 'exists in SPA, missing on MCP' item ranks BELOW any 'broken/blocking for everyone' item. MCP reach (#14) is strategic but not the acute need this week.
• Earn the durable promise now, even cheaply: Re-measure + Defend are Trevor's strategic core ('keep you one step ahead of the moving gap'). The lowest-cost down-payment is a deterministic compute-lift over the EXISTING snapshot store (captureSnapshot/getSnapshots already ship) — build it in Alpha; leave the expensive competitor-data Defend leg an honest Beta teaser.
• Decide meaning before exposing it: you cannot correctly bind an artifact whose definition is contested. Reconcile the two trigger artifacts (name the 6-type lever THE Decision Trigger; demote search-volume bands to a Workbook export column) BEFORE binding the trigger as an MCP tool. This is a load-bearing PRODUCT decision deserving Trevor sign-off, not a dev's inline guess.
• Forensic depth on the user's OWN evidence is the moat vs 'good-enough' generic AI: wire real ASIN evidence and re-key or deprecate generic prompt-in/assets-out tools (draft_asset). A generic copywriter shipped alongside a forensic engine muddies the 'this beats a ChatGPT prompt' credential.
• Terminology policy is enforced by a TEST, not a note: no Tier-C string (dominant_buyer_state, S1-S4, trigger TYPE names like Permission/Momentum, citations) appears in returned text OR structuredContent. Make redaction a single shared assertion gating every output-shaping item — the mirror surface doubles leak risk and is currently unprotected.
• Honesty over alarm-farming: PILLAR_TRIGGER maps every low pillar to a trigger, so the engine will ALWAYS surface a gap/trigger by construction. Add a confidence floor below which the tool returns 'no decisive gap found — your conversion problem is likely elsewhere.' Never fabricate precise lift numbers (labelled ranges only); kill the StayAheadScreen 58→71 hardcode.
• Don't pay for a paywall you can't afford: monetization is 100% unbuilt and the forensic read is ~8 Sonnet calls. A per-user cost/credit guardrail is a PRECONDITION gate on shipping free-core forensic, sequenced BEFORE anonymous exposure — not a parallel backlog line.
Executive summary
IDEA Brand Coach is a CONVERSION FIXER, not a brand-strategy tool, and its ~42-tool MCP surface (live on main; this checkout is behind) already covers the acquisition half of the loop (Diagnose → Analyse → Fix) but leaks brand-strategy framing at high-traffic seams and leaves the retention half (Re-measure → Defend) — the half Trevor elevated as the durable promise and the subscription reason — almost entirely un-tooled. The SINGLE BIGGEST MOVE: kill the generate_brief no_canvas homework wall (rank 1) — verified on main that generateBrief.ts already reads the avatar S1/S3/S4 artifacts (L193-196) but only AFTER it hard-returns reason:'no_canvas' at L182, so this is a cheap gate-reorder (rescoped M→S), not a new build, and it is the single highest-frequency P1-Maya failure: every paid session today ends in canvas homework, the exact brand-strategy friction Trevor #1 forbids. The second strategic correction (from the adversarial review, verified in code): the plan over-indexed on 'on Trevor's own connector it cannot be produced' and front-loaded MCP-surface bindings ahead of fixes that hit every tester in the SPA this week — so MCP bindings are demoted BELOW the SPA-facing reframes, and the trigger artifacts must be RECONCILED (decide what 'the Decision Trigger' is) BEFORE the trigger is bound as a tool, since avatarS3Triggers.ts emits search_terms/estimated_volume_band while the live identify-decision-trigger edge fn emits dominant_type/brand_anchor/evidence_phrases/placement — two unlinked artifacts. The third correction: Re-measure (Trevor #3, the durable promise) is promoted into the Alpha P0 cluster, because captureSnapshot/getSnapshots already exist on ITrustGapSnapshotService and only a deterministic compute-lift method is missing — the cheapest possible down-payment on the comeback engine; an Alpha that ships Diagnose→Analyse→Fix but cannot compute one re-measure delta has not earned the subscription reason. WHAT TO CUT/DEFER: (1) DEFER the free Trust Gap as an MCP tool to Beta — the free self-report lead magnet ALREADY works in the SPA where testers land, so an MCP version is N-of-1 connector reach AND it opens an anonymous-cost hole; (2) DEPRECATE/flag draft_asset from the Alpha surface — verified a verbatim generic-copy wrap of brand-copy-generator, not keyed to the user's own evidence or the named trigger, the commodity surface Trevor #12 warns is going 'good enough'; (3) do NOT build the Defend/competitor leg in Alpha (unbound edge fns + broken monolith = a Beta-sized data+cost project) — honest 'Brand Defence is coming' teaser only. Hard precondition: a per-user forensic-read cost guardrail (~8 Sonnet calls/read, zero monetization on main) must land BEFORE any anonymous free-core forensic exposure. Two live SPA-facing fabrications get named Alpha tasks regardless of MCP work: the StayAheadScreen.tsx L75 hardcoded 58→71 lift number, and a shared Tier-C redaction test gating every output-shaping item.
Legend
Priority: P0 (do now) · P1 · P2 · P3 (later). Phase: Alpha (live conversion fix) · Beta (retention) · Roadmap. Effort: S/M/L/XL. Type: build-new · wire-existing · extend · reframe · curate · deprecate · keep.

## Prioritized Backlog
Prioritized Backlog — best-first
Rank | Priority | Phase | Name | Type | Loop stage | ICP | What it does | Customer need (job-to-be-done) | Trevor alignment | Status | Effort | Dependencies | Why now | Risk if skipped
1 | P0 | Alpha | generate_brief: Signature/Avatar-only degrade path (kill the no_canvas homework wall) | reframe | Fix | P1 | Reorder generate_brief so it produces the 7-slot brief from a chosen Signature + Avatar S1/S3/S4 when no Brand Canvas exists, instead of hard-returning no_canvas. | P1 Maya who just got a Trust Gap + the one trigger needs a shippable brief TODAY; today the brief HARD-requires a brand_canvas, which requires a chosen Signature + full avatar pipeline — that IS homework. For P2 Rico the same degrade should SCAFFOLD ('here is the brief; here is the canvas you would build next to deepen it') — same substance, different delivery. | Directly serves the L1 promise ('the one fix today') and P1-compress (ends on one action, never homework); P2-scaffold teaching seam. Keeps the brief trigger-grounded (S3) so it stays a conversion fix, not a strategy exercise. | VERIFIED on origin/main: runGenerateBrief returns reason:'no_canvas' at generateBrief.ts L182; the S1/S3/S4 reads (avatar_s1_vocab/avatar_s3_triggers/avatar_s4_objections) ALREADY exist at L193-196 but sit BEHIND that gate. The this_week_tester_plan claim that it 'degrades to Signature+Avatar' is NOT in the code. | S | export-brief edge fn must accept canvas:null and render from S1/S3/S4; product-claims slot #6 fabrication gate still applies; relaxed grounding ref in the contract. Plumbing already present — this is a gate-reorder. | Highest-frequency P1 failure on the core loop; without it the 'shippable today' promise dies at the last step. Cheapest highest-leverage Alpha fix (rescoped M→S after code verification). | Every P1 session ends in canvas homework — the exact brand-strategy-tool friction Trevor #1 forbids; testers conclude the product cannot actually hand them a fix.
2 | P0 | Alpha | Kill the StayAheadScreen 58→71 hardcoded lift number | reframe | Re-measure | both | Remove the fabricated precise 58→71 lift on StayAheadScreen and replace with a labelled range or a 're-measure to see your lift' placeholder. | Testers landing in the SPA this week see a hardcoded, fabricated conversion-lift number presented as if real — it directly violates 'labelled ranges only' and erodes the 'I have seen this, here is the truth' credibility (#2). | #2 (no fabrication, trustworthy specifics) and the honesty-over-alarm-farming principle. A fake precise number is the fastest way to lose the credibility the credential is meant to earn. | VERIFIED: StayAheadScreen.tsx L75 hardcodes '58 → 71'. Live SPA-facing. | S | None — single-component copy/markup change. Naturally pairs with rank 4 (compute-lift) which can later feed a real number here. | Tiny, live, SPA-facing, higher real-customer risk than several ranked MCP items; testers see it this week. | A fabricated lift number on the retention screen contradicts the product's own anti-fabrication stance the moment a tester looks closely.
3 | P0 | Alpha | Reframe onboard_choose/onboard_panel + run_trust_gap output to open on the commercial wound | reframe | Diagnose | both | Repoint the front door from 'Simple Diagnostic vs Full Contextual Upload' (process) to the conversion wound ('Your listing isn't converting like the category — let's find why and the one fix'), and make run_trust_gap's first returned sentence open on that wound too. | The first touch on BOTH front doors (SPA menu + connector) must land as a conversion-fixer, not a brand questionnaire — open on a number the seller already owns. | #1 (conversion-fixer not brand-strategy) + Recognition-first (#4) + Skill 03. The literal current copy sounds like brand-strategy onboarding — the exact differentiation loss #1 warns of. | VERIFIED on main: onboard.ts L43/L49 literally label paths 'Simple Diagnostic' / 'Full Contextual Upload' (both STUBS); path enum diagnostic¦upload. run_trust_gap instruction is 'Never infer, default, or invent' with no wound framing in its return text. | S | None — copy/prose change in onboard.ts + server INSTRUCTIONS block + run_trust_gap result text; no schema change. Paired so the FIRST returned sentence on both front doors opens on the wound. | First impression on both surfaces; trivial effort, outsized framing payoff; gates the credibility of everything downstream. | The very first line tells testers this is a brand-strategy tool — kills differentiation before the engine ever runs.
4 | P0 | Alpha | compute_trust_gap_lift: deterministic re-measure delta over the existing snapshot store | build-new | Re-measure | both | Add a deterministic compute-lift/compare method (and an MCP/service hook) over the existing trust_gap_snapshots, returning a LABELLED lift range between a baseline and a re-measure — the first turn of the comeback loop. | Down-payment on Trevor's durable promise: a seller who applied the fix wants to see whether the gap moved. Today this is memory-narrated with a fake number; nothing computes a delta. | #3 (the durable promise / retention engine — 'keep you one step ahead of the moving gap') and the 'minimum that delivers the fix AND the first turn of the comeback loop' reframe. This is what converts Alpha from one-shot fixer to comes-back engine. | VERIFIED: ITrustGapSnapshotService has captureSnapshot + getSnapshots but NO compare/delta/lift method; SupabaseTrustGapSnapshotService implements both. The substrate exists; only the deterministic compare is missing. | M | Existing snapshot service (capture+get already implemented); a baseline-vs-latest compare fn; labelled-range output (never a fabricated precise number); can feed rank 2's StayAhead placeholder once real. | Cheapest strategic earn on the subscription reason; the substrate already exists so the marginal cost is one deterministic method. Leaving it below P2 scaffolding contradicts governing principle 4. | Alpha ships a one-shot fixer with no reason to come back; the retention loop stays narrated, not computed — the subscription reason is never earned.
5 | P0 | Alpha | Reconcile the two trigger artifacts (s3 search-bands vs named 6-type lever) | reframe | Analyse | both | Declare the named 6-type lever (identify-decision-trigger) THE Decision Trigger; demote avatar-triggers search-volume bands to a Workbook-A export column, not the customer-facing trigger. Requires Trevor sign-off. | Be handed the ONE Decision Trigger (named, anchored, evidenced) — not a search-volume table that reads like SEO/keyword tooling. | #1 and Skill 09: the Decision Trigger is the single primary conversion lever — three-component panel, no dropdown, no confidence score. The named lever IS the product; the bands are an export detail. The reframe is the difference between reading as SEO tooling and reading as a conversion-fixer — a load-bearing product decision, not a tidy-up. | VERIFIED collision: avatarS3Triggers.ts emits trigger_moment/search_terms/estimated_volume_band; identify-decision-trigger edge fn emits dominant_type/brand_anchor/evidence_phrases/placement (6 triggers, Dove/Harvard/Amazon's-Choice anchors). They are unlinked and the pipeline only knows the former. | S | Trevor decision on s3 contract shape; gates rank 6 (cannot bind a contested artifact). No schema migration if bands stay an export-only column. | Prerequisite framing for binding the trigger; without it the bound tool and the pipeline disagree on what 'trigger' means, and the search-band table leaks as the hero output. | Permanent artifact ambiguity; the search-band table leaks as the hero output, reading as SEO/keyword tooling rather than a conversion lever.
6 | P1 | Alpha | Bind the named Decision Trigger as an MCP tool (identify-decision-trigger) | wire-existing | Analyse | both | After reconciliation, expose the ONE Decision Trigger (6 types, Dove anchor, verbatim evidence, placement) on the MCP surface by binding the live identify-decision-trigger edge fn. | On the Claude/MCP connector Trevor uses, the product's hero output currently cannot be produced as a discrete artifact; binding adds connector reach. (The trigger ALREADY fires in the live SPA path, so this is reach, not the acute customer need.) | #14 (MCP is a real surface Trevor uses) and #1 (the Decision Trigger IS the conversion fix). Strategic reach, correctly sequenced AFTER the SPA-facing reframes and AFTER reconciliation. | VERIFIED: identify-decision-trigger edge fn is live (6 triggers, corrected Dove anchor, returns dominant_type/brand_anchor/evidence_phrases/placement) but referenced ONLY in src/mcp/evals/triggerOutput.ts — never bound in server.ts. | M | Rank 5 (reconciliation) MUST land first; avatar s1/s2 artifacts as optional grounding; gateWrite + requireOwnedAvatar pattern; the shared redaction test (rank 7). | Demoted below the everyone-affected SPA fixes per customer-need ordering; still in Alpha because the connector is Trevor's demo surface and the hero output should be reachable there once its meaning is settled. | The headline differentiator stays unreachable on the connector and the s3 search-band artifact keeps getting mistaken for 'the trigger'.
7 | P0 | Alpha | Shared Tier-C redaction conformance TEST gating every output-shaping item | build-new | Analyse | both | A single shared assertion (a real test, not a note) that no Tier-C string (dominant_buyer_state, S1-S4, trigger TYPE names, citations) appears in returned text OR structuredContent across all output tools. | Trevor #6 forbids Tier-C internals in user-facing output; the mirror/fallback surface doubles the leak risk and is currently unprotected — every output-shaping change risks leaking engine internals. | #6 (3-tier terminology, non-negotiable). Making redaction a shared gate rather than a per-item afterthought is the only reliable guard. | VERIFIED conceptually: the structured fallback/mirror pattern returns content twice (text + structuredContent), doubling leak surface; no shared redaction assertion exists. (The exact src/mcp/structuredFallback.ts path the review cited was NOT found at root on main — the mirror risk is real but treat the file path as unconfirmed; locate the actual fallback shaper during build.) | S | Locate the actual fallback/mirror shaper; applies to ranks 1,3,4,5,6 outputs. Build alongside the first output-shaping item. | Non-negotiable per #6 and currently unguarded; cheap to add as a shared assertion and it de-risks every other output item in this Alpha. | Any output-shaping change can leak buyer-state names / S1-S4 / citations into user-facing text — a direct Trevor #6 violation shipped to testers.
8 | P1 | Alpha | Honest 'no decisive gap / no trigger' verdict path (anti-alarm-farming floor) | extend | Analyse | both | Add a confidence/floor threshold below which run_trust_gap and the trigger derivation return 'no decisive gap found — your conversion problem is likely elsewhere' instead of always surfacing a dominant gap/trigger. | A product that can never say 'your listing is actually fine here' burns the 'I've seen this, here's the truth' credibility; PILLAR_TRIGGER maps every low pillar to a trigger so the engine ALWAYS finds one by construction. | #2 ('I know what this is, I've seen it before') and the honesty principle. A trustworthy no-gap verdict is what makes the gap verdicts believable. | VERIFIED: identify-decision-trigger's PILLAR_TRIGGER maps every low pillar to a trigger and the engine selects exactly one dominant trigger by construction; run_trust_gap always returns a primary gap. No floor/no-gap path exists. | M | A confidence/floor threshold on the derivation + on the trust-gap primary-gap routing; honest copy for the no-gap branch. | First-class Alpha item (not a footnote) because the alarm-farming-by-construction is baked into the live derivation testers will hit. | The engine fabricates a gap/trigger even when the corpus doesn't support one, undermining the credibility the whole product rests on.
9 | P0 | Alpha | Per-user forensic-read cost guardrail (PRECONDITION gate before any anonymous free-core forensic) | build-new | Diagnose | both | A per-user cost/credit ceiling on the ~8-Sonnet-call forensic read, enforced BEFORE any anonymous free-core forensic exposure ships. | Monetization is 100% unbuilt and the forensic read is ~8 Sonnet calls; exposing free-core forensic to anonymous callers without a ceiling is an open wallet. | Enables the two-phase Trust Gap (#8) to ship safely; protects the business that funds the durable promise. A precondition, not a feature. | VERIFIED: no payment dependency; paywall is a UI stub; forensic read is ~8 Sonnet calls (runtime cost model). No credit ceiling exists. | M | Per-caller usage counter/ceiling; sequenced BEFORE any anonymous free-core forensic path. Gates anything that exposes forensic compute without auth. | It is a sequencing PRECONDITION: the moment free-core forensic is reachable anonymously, the wallet is open. Build the ceiling first. | Anonymous callers can run unbounded ~8-Sonnet-call forensic reads with zero monetization — an unbounded cost-abuse hole.
10 | P1 | Alpha | Wire ingest_evidence ASIN auto-pull (real /dp/ evidence, replace the stub) | build-new | Diagnose | P1 | Replace the 'NOT YET WIRED' ASIN stub with a real /dp/ listing + reviews pull so most P1 sessions get real evidence instead of staying in inference mode. | P1 Maya pastes an ASIN expecting the engine to read her real listing/reviews; today it returns a stub note and the session stays in inference mode, weakening the forensic moat. | #12 (forensic depth on the user's OWN evidence is the moat vs 'good-enough' generic AI) and #10 (thin-corpus handling needs real corpus first). Real evidence is what lets the engine quote verbatim. | VERIFIED: ingestEvidence.ts L12/L47/L126 explicitly mark asin as 'NOT YET WIRED — returns a stub note (no fabrication).' NOTE: the TOOL SURFACE preamble claims 'asin review auto-pull LIVE 2026-06-25' — that is NOT true on main; main still stubs it. Reconcile this discrepancy before build. | L | Proven /dp/ parser (exists in infinityvault core-os per memory); evidence_snapshots write path already present; cost guardrail (rank 9) since scraping + forensic compounds cost. | Without real evidence, P1 sessions stay inferential and the forensic differentiation is weaker than claimed; but it is L-effort and depends on the cost guardrail, so it sits below the cheap framing/retention fixes. | The product keeps inferring instead of quoting the seller's own reviews — the exact 'good-enough generic AI' parity Trevor #12 warns erodes the moat.
11 | P1 | Alpha | Re-key or flag draft_asset off the Alpha surface (deprecate the generic copywriter) | reframe | Fix | both | Either re-key draft_asset to be trigger/evidence-grounded (then it earns its place) or hide it behind a flag for Alpha — stop shipping a generic prompt-in/assets-out copywriter alongside the forensic engine. | A generic copy generator not keyed to the user's own evidence or the named trigger is commodity; shipping it next to a forensic engine muddies the 'this beats a ChatGPT prompt' credential. | #12 (generic prompt-in/assets-out AI is going 'good enough' — differentiation = forensic depth) and #5 (the credential must be visibly earned by output beating a ChatGPT prompt). | VERIFIED: draft_asset still registered (server.ts L110); draftAsset.ts is a 'VERBATIM wrap of the existing brand-copy-generator edge fn' — generic copy, grounded in the KB server-side but NOT keyed to the named Decision Trigger or the user's verbatim evidence. | M | Either a trigger/evidence-keyed re-key (depends on rank 5/6 trigger artifact) or a feature flag to hide it in Alpha. | Cheap to flag-off now; re-keying can follow the trigger reconciliation. Keeps the Alpha surface forensic, not commodity. | A generic copywriter on the Alpha surface signals the product is interchangeable with a ChatGPT prompt, undercutting the credential.
12 | P2 | Beta | score_trust_gap_free: expose the FREE self-report diagnostic as an MCP tool | build-new | Diagnose | both | A no-auth MCP tool running the 4 evidence-based observe-your-listing questions returning /100 + primary gap + plain explanation, NO trigger — the lead magnet on the connector. | Free, fast gap read for users entering via the connector. But the free self-report ALREADY works in the SPA (FreeDiagnostic.tsx / diagnosticQuestions.ts) where testers actually land — the MCP version is N-of-1 connector reach. | Realises the two-phase Trust Gap (#8) as MCP surface and #14, but it is NOT the acute customer need this week and it opens the anonymous-cost hole (rank 9 must precede it). | VERIFIED: run_trust_gap is pure compute ('Never infer, default, or invent'); the 4 questions live only in diagnosticQuestions.ts/FreeDiagnostic.tsx. The free hook is NOT absent for customers — only for the connector. | M | Reuse diagnosticQuestions + buildTrustGap; MUST NOT emit a trigger (paygate); MUST sit behind the rank-9 cost guardrail; anonymous-safe. | DEFERRED to Beta per the adversarial review: the lead magnet already serves customers in the SPA; building it on MCP this week is reach for an N-of-1 surface and is the item that opens the anonymous open-wallet. | No free hook on the connector specifically — but customers entering via the SPA are unaffected, so the customer-facing funnel top is intact.
13 | P2 | Beta | Defend leg: honest 'Brand Defence is coming' teaser only (do NOT build in Alpha) | reframe | Defend | both | Keep Defend an honest teaser in Alpha; the competitor-watch subscription leg is a Beta-sized data+cost project — do not bind the broken/unbound competitor fns now. | The subscription reason long-term is competitor-watch ('the gap is always moving'), but delivering it requires competitor data sourcing, cost controls, and a working orchestrator — none Alpha-ready. | #3 and #11 (Defend = the retention engine / the management layer) — but honestly teased, not faked. Affirms the plan's correct cut. | VERIFIED context: competitor-discovery + competitive-analysis-orchestrator edge fns exist UNBOUND; the old monolith is broken (contract mismatch, gpt-4o, P2 flag). Binding them is Beta-sized. | S | None for the teaser. The real build depends on competitor data sourcing (DataForSEO/Keepa), counsel review, and cost controls — all Beta. | An honest teaser sets the comeback expectation without faking capability; building the leg now would blow Alpha scope on a data+cost project. | Promising Defend without an honest teaser would either fake capability (alarm-farming) or blow Alpha scope — both worse than an honest 'coming next.'

## Phasing Roadmap
Phasing — Alpha / Beta / Roadmap swimlanes
Phase | Theme | Items | Exit criteria
Alpha P0 (this-week core loop — SPA-first) | Make the free→paid conversion-fix loop excellent for P1 in the SPA, earn the first turn of the comeback loop, and protect the wallet — before any MCP-surface reach. | • Rank 1 — generate_brief Signature/Avatar degrade (kill the no_canvas homework wall; gate-reorder) • Rank 2 — kill the StayAheadScreen 58→71 hardcoded lift • Rank 3 — reframe onboard + run_trust_gap output to open on the conversion wound • Rank 4 — deterministic compute-lift over the existing snapshot store (labelled range) • Rank 5 — reconcile the two trigger artifacts (Trevor sign-off: named lever = THE trigger; bands → Workbook column) • Rank 7 — shared Tier-C redaction conformance test • Rank 9 — per-user forensic-read cost guardrail (precondition for any anonymous free-core forensic) | A P1 session runs Diagnose→Analyse→Fix end-to-end with NO canvas homework and ENDS on one action; the front door's first line is the conversion wound, not a process menu; a re-measure produces a deterministic labelled lift range with NO fabricated numbers on screen; the trigger's meaning is signed off; the redaction test passes (no Tier-C strings in text or structuredContent); the cost guardrail enforces a per-user ceiling. Run npm test / tsc --noEmit / lint green.
Alpha P1 (depth + connector reach, after P0) | Bind the hero output on Trevor's connector now that its meaning is settled, deepen forensic evidence, harden honesty, and de-commoditise the surface. | • Rank 6 — bind the named Decision Trigger as an MCP tool (after reconciliation + redaction test) • Rank 8 — honest 'no decisive gap / no trigger' verdict floor • Rank 10 — wire ingest_evidence ASIN auto-pull (real /dp/ evidence; reconcile the LIVE-vs-stub doc discrepancy) • Rank 11 — re-key or flag-off draft_asset (de-commoditise the Alpha surface) | The Decision Trigger is producible as a discrete artifact on the MCP connector and passes the redaction test; the engine can honestly return 'no decisive gap' below the confidence floor; a pasted ASIN yields real listing+reviews (or an honest stub note, never fabrication); draft_asset is either trigger/evidence-keyed or hidden behind a flag in Alpha.
Beta | Realise the full retention engine and the connector lead magnet once monetization + cost controls + competitor data are in place. | • Rank 12 — score_trust_gap_free as a no-auth MCP tool (behind the cost guardrail; no trigger emitted — paygate intact) • Rank 13 → real build — Defend / competitor-watch leg (competitor data sourcing + orchestrator + counsel review + cost controls) • Monetization / paywall (100% unbuilt on main) — the gate that funds the durable promise • Demographics → Brand Context layer for Beta targeting (Avatar 2.0 stays demographics-free) | The free lead magnet is reachable on the connector without opening a cost hole; competitor-watch produces a real, cost-controlled, counsel-reviewed signal that powers the subscription reason; the paywall enforces the two-phase Trust Gap (free self-report vs paid forensic).

## Coverage Matrix
Loop stage x ICP — current coverage, gap, planned fix
Loop stage | ICP | Current coverage | Gap | Planned fix
Diagnose | P1 | run_trust_gap (compute-only) + free self-report in SPA (FreeDiagnostic.tsx); onboard_choose front door. | Front door opens on process language ('Simple Diagnostic vs Full Contextual Upload'), not the conversion wound; ASIN evidence is a stub so sessions stay inferential; no cost ceiling on forensic compute. | Rank 3 (reframe both front doors to the wound), rank 10 (wire ASIN evidence), rank 9 (cost guardrail precondition).
Diagnose | P2 | Same diagnostic engine; coach can teach the 4 IDEA dimensions one at a time. | Same process-language front door; no scaffolded 'why' framing on entry for the time-rich VA. | Rank 3 front-door reframe (shared); P2 teaching framing carried through generate_brief scaffold variant (rank 1) and reusable checklist outputs.
Analyse | both | identify-decision-trigger edge fn LIVE in the SPA path (6 triggers, anchors, verbatim evidence, placement); avatar build_avatar_stage s3. | Two unlinked trigger artifacts (search-bands vs named lever) — meaning contested; the hero output is not bound on the MCP connector; PILLAR_TRIGGER always finds a trigger (no honest no-gap path); Tier-C leak risk in mirrored output. | Rank 5 (reconcile, Trevor sign-off) then rank 6 (bind on MCP); rank 8 (no-decisive-gap floor); rank 7 (shared redaction test).
Fix | P1 | generate_brief produces the 7-slot brief; generate_canvas; draft_asset (generic copy). | generate_brief HARD-blocks with no_canvas (homework wall) despite already reading S1/S3/S4 behind the gate; draft_asset is a generic non-evidence-keyed copywriter (commodity). | Rank 1 (gate-reorder degrade to Signature+Avatar, ends-on-one-action); rank 11 (re-key or flag-off draft_asset).
Fix | P2 | Same brief/canvas tools. | No scaffolded 'here is the canvas you'd build next' teaching variant of the degraded brief for the time-rich VA. | Rank 1 P2 variant: same degrade, optionally scaffold the next-step canvas as a teaching seam.
Re-measure | both | trust_gap_snapshots table + SupabaseTrustGapSnapshotService (captureSnapshot + getSnapshots). | NO compare/delta/lift method — the retention loop is memory-narrated; StayAheadScreen shows a FABRICATED 58→71 lift number. | Rank 4 (deterministic compute-lift over the existing snapshot store, labelled ranges); rank 2 (kill the 58→71 hardcode, feed the real range once available).
Defend | both | competitor-discovery + competitive-analysis-orchestrator edge fns exist but UNBOUND; old monolith broken/hidden. | Zero MCP tools; no working competitor-watch; the subscription reason is un-delivered. | Rank 13 (honest 'coming' teaser in Alpha); real build deferred to Beta (competitor data sourcing + cost controls + counsel review).

## Planned vs Needed
Planned-vs-Needed challenge — build / cut / reframe / defer / keep
Item | Verdict | Reason
generate_brief no_canvas hard block (plan rank 1, effort M) | build | Keep as #1 but RESCOPE M→S: verified on main that the S1/S3/S4 avatar reads already exist at generateBrief.ts L193-196, sitting BEHIND the L182 no_canvas return. The degrade is a gate-reorder, not new plumbing — both the highest-impact AND cheaper than the plan assumed.
Bind Decision Trigger as MCP tool ABOVE reconciliation (plan rank 2) | defer | Demote below the SPA-facing reframes AND below reconciliation. The trigger ALREADY fires in the live SPA path; binding only adds N-of-1 connector reach. And you cannot correctly bind an artifact whose meaning is contested (avatarS3Triggers vs the edge fn) — reconcile first. New order: reconcile (rank 5) → bind (rank 6).
Reconcile the two trigger artifacts (plan rank 3, inline 'S') | reframe | Promote ABOVE the MCP binding and treat as a load-bearing PRODUCT decision needing Trevor sign-off, not a dev's inline guess. Demoting search-volume bands to a Workbook column vs naming the 6-type lever is the difference between reading as SEO tooling and as a conversion-fixer (#1).
score_trust_gap_free as an MCP tool in Alpha (plan rank 5) | defer | DEFER to Beta. The free self-report lead magnet ALREADY works in the SPA where testers land; building it on MCP is N-of-1 reach AND it opens the anonymous open-wallet (it is the item that exposes ~8-Sonnet forensic-adjacent cost without a ceiling). Not an acute customer need this week.
Re-measure snapshot+compute-lift (plan: trailing P1/P2 scaffolding) | build | PROMOTE into the Alpha P0 cluster (rank 4). captureSnapshot/getSnapshots already exist; only a deterministic compare is missing — the cheapest down-payment on Trevor's elevated durable promise (#3). An Alpha that can't compute one re-measure delta hasn't earned the subscription reason.
draft_asset on the Alpha surface (server.ts L110) | cut | DEPRECATE or re-key for Alpha. Verified a verbatim wrap of brand-copy-generator — generic prompt-in/assets-out copy not keyed to the user's own evidence or the named trigger. It is the commodity surface Trevor #12 warns is going 'good enough' and it muddies the 'beats a ChatGPT prompt' credential (#5).
Defend/competitor leg in Alpha | cut | Affirm the plan's cut. competitor-discovery + competitive-analysis-orchestrator are unbound and the old monolith is broken; binding is a Beta-sized data+cost project. Honest 'Brand Defence is coming' teaser only in Alpha.
StayAheadScreen 58→71 hardcoded lift | build | Add as a NAMED Alpha task (the plan buried it). Verified L75 hardcodes a fabricated precise lift number shown to testers this week — it directly violates the plan's own 'labelled ranges only' principle and is tiny + live SPA-facing.
Per-user forensic-read cost guardrail (plan: last/parallel line) | build | Reframe as a HARD PRECONDITION gate, not a parallel backlog item. ~8 Sonnet calls/read with zero monetization and zero ceiling is an open wallet the moment any anonymous free-core forensic ships. Sequence the guardrail BEFORE anonymous exposure.
Tier-C redaction (plan: per-item afterthought) | build | Add a SHARED redaction TEST gating every output-shaping item. The mirror/fallback surface doubles the leak risk Trevor #6 forbids and is currently unprotected; per-item notes are not a reliable guard. (Locate the actual fallback shaper — the cited src/mcp/structuredFallback.ts path was not found at root on main.)
Honest no-gap / no-trigger verdict (plan: single flag) | build | Add as a first-class Alpha item. PILLAR_TRIGGER maps every low pillar to a trigger and the engine selects exactly one by construction — it can never say 'your listing is fine here.' A confidence floor protects the 'I've seen this, here's the truth' credibility (#2).
ingest_evidence ASIN auto-pull | build | Keep in Alpha but rank below the cheap framing/retention fixes (L-effort, depends on the cost guardrail). NOTE a documentation discrepancy: the TOOL SURFACE preamble claims 'asin auto-pull LIVE 2026-06-25' but main still returns the 'NOT YET WIRED' stub (ingestEvidence.ts L12/47/126) — reconcile before building.

## Open Questions
Open questions — the calls only Matthew / Trevor can make
1 | Trigger reconciliation (rank 5) needs explicit Trevor sign-off: confirm the named 6-type lever (identify-decision-trigger) IS 'the Decision Trigger' and the avatarS3Triggers search-volume bands are demoted to a Workbook-A export column only — NOT the customer-facing trigger. This is a product decision, not a dev guess.
2 | Documentation discrepancy to reconcile before building rank 10: the TOOL SURFACE preamble states 'asin review auto-pull LIVE 2026-06-25', but origin/main ingestEvidence.ts (L12/47/126) still returns the 'NOT YET WIRED' stub. Which is ground truth — was ASIN auto-pull shipped on another branch and not merged to main, or is the preamble aspirational?
3 | Compute-lift (rank 4) output shape: confirm labelled-range bands (never a precise fabricated number) and which baseline the delta compares against (first snapshot vs last vs a named milestone) before it feeds the StayAhead placeholder.
4 | Cost guardrail (rank 9) ceiling policy: per-user credit count, hard cap, or soft warn? And does it gate the authenticated forensic read in Alpha P0, or only the anonymous free-core path when rank 12 ships in Beta?
5 | Redaction shared shaper location: the cited src/mcp/structuredFallback.ts path was not found at the repo root on main — identify the actual fallback/mirror shaper that returns structuredContent so the shared redaction test wraps the real surface.
6 | draft_asset (rank 11): re-key to trigger/evidence-grounding (more work, earns its place) OR flag-off for Alpha (cheap, revisit in Beta)? Depends on how soon the trigger artifact (rank 5/6) stabilises.
7 | P2 (Rico) scaffold variant of the degraded brief (rank 1): confirm the teaching seam ('here is the canvas you'd build next') is in Alpha scope or deferred — the plan treated the degrade as P1-only.

## Tool Inventory (ref)
Current MCP tool surface (reference) — src/mcp/server.ts
Tool(s) | Group | Purpose
health | Gateway | Liveness + config probe
list_assets / get_asset / get_asset_history | IV-OS reads | Asset ledger reads + change log
log_asset / update_asset_status / record_assessment | IV-OS writes | Asset lifecycle + assessment (identity-gated)
generate_concepts / publish_filter_check / draft_asset / design_test | Asset chain (Fix) | Concept->safety-gate->draft->A/B test spec
run_trust_gap | Diagnose | Trust Gap(TM) 4-dimension scorecard (free self-report)
run_diagnostic_evidence | Analyse | Evidence-grounded forensic diagnostic (paid)
build_avatar_stage | Analyse | Avatar 2.0 S1-S5 (s3 holds the Decision Trigger(TM))
ingest_evidence | Analyse | Persist listing + reviews; asin auto-pull LIVE
get_context_status / provide_context | Context | 18-slot fill-map + write-back
generate_canvas / generate_brief / generate_audit_idea_map | Fix/Output | Brand Canvas / Export Brief / Audit x IDEA map
run_marketing_audit / export_workbook | Output | Workbook B investment matrix / gold .xlsx export
generate_signature / persist_signature | Signature | Signature options + persist
create_avatar/list_avatars/get_avatar/set_current_avatar/set_primary_avatar/record_avatar_build/set_context_avatars | Avatar lifecycle | Avatar CRUD + context switching
list_funnel_inventory/upsert_funnel_touchpoint/run_funnel_audit/get_funnel_audit/get_funnel_assets/get_funnel_coverage | Funnel | Asset-Alignment-Studio substrate
list_coach_conversations / get_coach_conversation | Coach reads | Per-avatar chat history (retention)
submit_feedback | Feedback | User->team Slack feedback (anon ok)