## Summary
IDEA Brand Coach Gen 3 — Execution & Time Tracker
Generated 2026-05-25 · execution + effort view at strategic-objective grain · links to feature_status_tracker.xlsx by feature ID
Time invested by source
Source | Hours | Share
Logged (Clockify) | 9.78 | 52.77%
Meetings (Fathom, unlogged) | 2.7 | 14.57%
Estimated (agent sessions) | 6.05 | 32.66%
GRAND TOTAL | 18.53
Per-objective rollup
Objective | Status | Rollup % | Total Hours

## Time Log
Date | Source | Objective | Description | Hours | Note
2026-03-05 | meeting | O7 | Meeting: Impromptu Google Meet — pivot to conversational AI coach | 0.6 | Unlogged. Pivot decision + $500 acceleration. Est. from max summary ts ~2188s.
2026-03-05 | meeting | O7 | Meeting: Impromptu Zoom — refine value prop & IDEA workflow | 0.7 | Unlogged. IDEA framework workflow, chat-first canvas. Est. from max summary ts ~2336s.
2026-03-18 | meeting | O7 | Meeting: IDEA Brand Coach Sync Up | 1.4 | Unlogged. Skill-based model pivot, beta plan, cost analysis. Est. from max summary ts ~4939s.
2026-04-06 | logged | O7 | push to Lovable | 0.03
2026-04-06 | logged | O1 | Integrate Claude agent SDK | 0.17
2026-04-07 | logged | O3 | optimize extraction fields + field review flow | 0.14
2026-04-07 | logged | O3 | optimize extraction fields + field review flow | 0.25
2026-04-07 | logged | O1 | clean up broken text entry in chat, hardcoded text always appearing for suggested edits, push updated working app to Lovable & verify doc gen works | 0.76
2026-04-19 | logged | O7 | create marketing video in remotion | 0.03
2026-04-19 | logged | O7 | create marketing video in remotion | 0.24
2026-04-19 | logged | O7 | create marketing video in remotion | 0.08
2026-04-23 | logged | O7 | review Trevor's docs & meet with him to discuss next steps | 2.19
2026-04-24 | estimated | O7 | Agent session 53d8367d (-Users-matthewkerns-workspace-ecommerce-ecommerce-tools-brand-systems-idea-brand-coach, 52 events) | 0.633 | estimated from JSONL active time (15-min idle cap)
2026-04-24 | estimated | O7 | Agent session a754fbda (-Users-matthewkerns-workspace-ecommerce-ecommerce-tools-brand-systems-idea-brand-coach, 41 events) | 0.34 | estimated from JSONL active time (15-min idle cap)
2026-04-24 | logged | O7 | investigate obsidian and autoresearch | 0.2
2026-04-24 | logged | O7 | investigate obsidian and autoresearch | 0.25
2026-04-28 | logged | O7 | use the app for InfinityVault branding funnel spreadsheet build out | 0.03
2026-04-29 | logged | O7 | brand funnel capture | 0.21
2026-05-03 | logged | O7 | Message Trevor | 0.3
2026-05-03 | logged | O7 | map out ideal case study | 0.14
2026-05-03 | logged | O7 | map out ideal case study | 0.39
2026-05-05 | logged | O7 | Reply to Trevor, review his mock ups | 0.13
2026-05-06 | logged | O7 | Meet with Trevor | 1.35
2026-05-06 | logged | O7 | Make skill that manages brand workspace sheet | 0.17 | review: unmatched -> default O7
2026-05-13 | estimated | O7 | Agent session 752b7d11 (-Users-matthewkerns-workspace-ecommerce-ecommerce-tools-brand-systems-idea-brand-coach, 438 events) | 1.355 | estimated from JSONL active time (15-min idle cap)
2026-05-13 | logged | O7 | Review workbook, request dev agent progress report towards this planned outcome | 0.01
2026-05-13 | logged | O7 | Review workbook, request dev agent progress report towards this planned outcome | 0.03
2026-05-13 | logged | O7 | Review workbook, request dev agent progress report towards this planned outcome | 0.22
2026-05-13 | logged | O7 | Skim workbook with plan | 0.05
2026-05-13 | logged | O7 | build out spreadsheet with alpha beta and GA launch plan | 0.24
2026-05-13 | logged | O7 | Plan bare minimum beta readiness in a new thread with all available and relevant context - including my PRD | 0.01
2026-05-14 | estimated | O7 | Agent session e50443e0 (-Users-matthewkerns-workspace-ecommerce-ecommerce-tools-brand-systems-idea-brand-coach, 77 events) | 0.647 | estimated from JSONL active time (15-min idle cap)
2026-05-16 | logged | O7 | send follow up about brand coach feedback loop | 0.13
2026-05-16 | logged | O7 | review updated workbook | 0.23
2026-05-16 | logged | O7 | integrate top problems we're solving for the user into the workbook | 0.15
2026-05-16 | logged | O7 | message Trevor, update feature workbook, send him Launch Roadmap + Feature workbook | 0.43
2026-05-16 | logged | O7 | write out todos | 0.22
2026-05-16 | logged | O7 | review spreadsheet and plan reply to Trevor | 0.3
2026-05-17 | logged | O7 | Run Trevor‘s document through my Claude thread for the marketing plan for the quarter | 0.46
2026-05-18 | logged | O7 | Reply to Trevor in whatsapp | 0.19
2026-05-24 | logged | O7 | Ramp up on brand coach project - review all recent context (last 3-4 meetings, local codebase recent changes, review for organizational updates, agentic tooling updates, and agent instruction file hierarchy management | 0.05
2026-05-25 | estimated | O7 | Agent session 47cf9ccc (planning, 155 events) | 0.3 | estimated from JSONL active time (15-min idle cap)
2026-05-25 | estimated | O7 | Agent session 6c99fece (planning, 384 events) | 1.068 | estimated from JSONL active time (15-min idle cap)
2026-05-25 | estimated | O7 | Agent session 9b9fb0d5 (planning, 223 events) | 0.472 | estimated from JSONL active time (15-min idle cap)
2026-05-25 | estimated | O7 | Agent session 29a9c876 (tooling, 404 events) | 1.238 | estimated from JSONL active time (15-min idle cap)

## Objectives
ID | Objective | Linked Features | Description | Phase | Status | Rollup % | Hours Logged | Hours Meeting | Hours Estimated | Hours Total
O1 | Diagnostic & Trust Gap™ | F-001, F-002 | Layer 1 conversation: 10-question diagnostic + sidebar population/follow-up | Alpha | in_progress | 30%
O2 | Draft Canvas Synthesis | F-003 | Synthesize Layer 1 answers into a draft brand canvas | Alpha | in_progress | 42%
O3 | Customer Insight Engine / Avatar Builder | F-004, F-005, F-006 | Avatar Builder sections 1-4, AI assistance, confidence scoring & edit lock | Alpha/Beta | in_progress | 45%
O4 | The Signature & Coach Mode v2 | F-009 | Stage 5 retention output: brand voice guide, Amazon listing copy | Beta | in_progress | 45%
O5 | Export & Deliverables | F-007 | PDF / Word / Markdown export of brand strategy | Beta | in_progress | 72%
O6 | Monetization / Pay Gate | F-008 | Stripe pay gate before premium outputs | GA | not_started | 0%
O7 | Launch & Strategy | — | Alpha->Beta->GA gates, ideabrandcoach.com site, TikTok-conditional, Trevor sync, roadmap/context upkeep | All | in_progress | n/a
TOTAL

## Meetings
Date | Title | Recording ID | URL | Duration (h) | In Clockify? | Objective
2026-05-06 | Impromptu Zoom — Gen 3 mockup review | 144128256 | https://fathom.video/calls/664335828 | 1.35 | Y | O7
2026-04-23 | 4/23 IDEA Brand Coach Part 2 | 140691318 | https://fathom.video/calls/649154125 | 1.1 | Y | O7
2026-04-23 | 4/23 IDEA Brand Coach Part 1 | 140678453 | https://fathom.video/calls/649118151 | 1 | Y | O7
2026-03-18 | IDEA Brand Coach Sync Up | 130896361 | https://fathom.video/calls/605088052 | 1.4 | N | O7
2026-03-05 | Impromptu Google Meet — pivot to conversational AI coach | 127607831 | https://fathom.video/calls/590988739 | 0.6 | N | O7
2026-03-05 | Impromptu Zoom — refine value prop & IDEA workflow | 127583497 | https://fathom.video/calls/590934937 | 0.7 | N | O7
N = meeting time NOT in Clockify (added as 'meeting' hours). Y = already counted in Clockify (reference only).

## Sessions
Date | Session ID | Worktree | Events | Active (h, est.) | Objective
2026-05-25 | 47cf9ccc | planning | 155 | 0.3 | O7
2026-05-25 | 6c99fece | planning | 384 | 1.068 | O7
2026-05-25 | 9b9fb0d5 | planning | 223 | 0.472 | O7
2026-05-25 | 29a9c876 | tooling | 404 | 1.238 | O7
2026-05-14 | e50443e0 | -Users-matthewkerns-workspace-ecommerce-ecommerce-tools-brand-systems-idea-brand-coach | 77 | 0.647 | O7
2026-05-13 | 752b7d11 | -Users-matthewkerns-workspace-ecommerce-ecommerce-tools-brand-systems-idea-brand-coach | 438 | 1.355 | O7
2026-04-24 | 53d8367d | -Users-matthewkerns-workspace-ecommerce-ecommerce-tools-brand-systems-idea-brand-coach | 52 | 0.633 | O7
2026-04-24 | a754fbda | -Users-matthewkerns-workspace-ecommerce-ecommerce-tools-brand-systems-idea-brand-coach | 41 | 0.34 | O7
TOTAL
Active time = sum of inter-event gaps, capped at 15 min/gap. Under-counts: subagent work is not in top-level sessions.

## Change Log
Date | Version | Change
2026-05-25 | v1.0 | Initial build: 7 strategic objectives; time triangulated from Clockify (logged) + Fathom (meeting) + JSONL (estimated).