## Overview
Alpha Sprint 1 — Remainder & Tester-Invite Gate
IDEA Brand Coach · compiled 2026-06-19 from Slack, Fathom, WhatsApp, session transcripts, repo + memory
Field | Detail
Sprint | Alpha Sprint 1 (current)
Window | Through 2026-06-21 · testers onboard the week of 6/21 · compiled 2026-06-19
Sprint goal | Ship the updated single-focus interaction form so a NEW user can sign up, develop their brand with the coach, see their strategy, and use the Funnel Mapper to generate a design brief / prompt to start creating brand assets — live on prod and QA'd.
Core loop (what testers test) | sign up → develop brand with the coach → brand strategy → Funnel Mapper emits a design brief / prompt → create the asset
Definition of done | A brand-new user (desktop OR 375px mobile) signs up, lands on a screen that tells them what to do, develops their brand with the coach, sees their strategy, opens the Funnel Mapper from nav, and generates a copy-pasteable design brief + image prompt — end to end on prod, captured in PostHog.
Decision 1 — asset endpoint | Funnel adds a 'Generate design brief + image prompt' generator (hand to a designer / image-gen). NOT full in-app generation.
Decision 2 — FTUE scope | Ship the new single-focus UI shell + global nav + first-run landing + 375px fix (Matthew is wiring the new UI). The minimal version was the floor; the prototypes are the target.
Decision 3 — coach journey | Coach is good-enough (book-grounded, runs Trust Gap, cross-session memory, 21-tool loop) — make it discoverable, don't rebuild the conversation engine this sprint.
Prototypes (the target UI) | _bmad-output/mockups/: brand-coach-single-focus-app.html (interaction form) · brand-coach-funnel.html (brief/prompt generator) · brand-coach-strategy-document.html · brand-coach-ftue-mockup.html · brand-coach-module-variations.html
Update 6/19 — 3rd destination | Competitor Analysis promoted to its own top-level tab — 'Brand vs Competition' — that Brand Coach + Funnel Mapper PULL from (aligns with Trevor's 'Competitor Trust Gap Comparison' + his 'dedicated module / feeds the Canvas' intent). The prototype tab + funnel-as-loop are IN-FLIGHT in a parallel agent session (7034cdd6); the engine is already deployed behind a flag. See the 'Competitor Analysis (3rd Tab)' sheet.
Deploy reality | origin/main is the source of truth and is deployed to prod (manual frontend rsync; CI auto-deploy is OFF). Do NOT build/deploy from feat/alpha-instrumentation (105 behind main).
How to read this | Tab 2 = where the loop stands · Tab 3 = remaining work · Tab 4 = the gate that lets us invite · Tab 5 = metrics · Tab 6 = deferred roadmap · Tab 7 = risks.

## Core Loop Status
Core Loop — current state
What's built, half-built, or blocked across the loop testers will walk
Loop step | State | What exists today | Gap to close this sprint
1 · Sign up / sign in | ⚠ Live but buggy | Auth works; a friend completed signup+signin on 6/18. | Fix the sign-up/sign-in bugs the friend hit; confirm the tester email-confirmation path.
2 · Land & know what to do | 🔴 Broken UX | New user lands on /v2/coach with NO global nav; V1/V2 two-shell split; broken at 375px. Friend: 'what is this?' | New single-focus shell + nav + first-run landing + mobile fix.
3 · Develop brand w/ coach | ✅ Live & strong | /v2/coach: book-grounded (150+ IDEA skills), real Trust Gap, cross-session memory, 21-tool loop, 11 chapters/~49 fields w/ provenance. | Re-render as single-focus (needs-you vs auto-managed); add alerts + readiness signals.
4 · Brand strategy artifacts | ✅ Built | Signature, Canvas, Avatar, Export Brief, Audit×IDEA all exist as tools + ledger; 13-section strategy doc exports. | Small: include the Signature in the exported strategy doc (currently omitted).
5 · Funnel tool | ✅ Live & on main | /v2/funnel: upload → vision audit vs avatar+Signature → map/coverage → fix-with-coach writes copy; bulk upload. | It has NO nav link (dangling route) — make it reachable; reorganize by funnel stage.
6 · Funnel → design brief / prompt | ⚠ Partial — the open end | generate_brief already emits a 7-slot image brief + listing copy + PPC tiers — but MCP-only, not in the funnel UI. Paste-ready external-tool prompt does NOT exist yet. | Surface generate_brief in the funnel + a thin prompt layer (over brief slots + generate_concepts); Canvas-degrade fallback.
7 · Competitor Analysis (Brand vs Competition) | ⚙ Prototype in-flight; engine deployed (dark) | Per-touchpoint competitor engine (competitor-analysis-asset, IDEA-scored) deployed ACTIVE behind VITE_COMPETITOR_AGENTS=OFF; funnel UI panels built on the feat/competitor-agents worktree (not on main). | Promote to a 3rd destination + a brand-level 'you vs competitors (4 pillars)' view + pull-seams into Coach/Funnel. Roadmap — NOT a tester gate.

## Sprint Backlog (Remaining)
Remaining work — Alpha Sprint 1
Type: Fix / Net-new / Reskin (over built code) / Process · Owner is a suggested split (Matthew=UI, Claude=backend+metrics) · Gate = which invite gate it satisfies
ID | Area | Task | Wires to (real code / tool) | Type | Effort | Owner | Depends | Done-when (verify) | Gate
A1 | Auth | Reproduce + fix the sign-up / sign-in bugs the friend hit (6/18) | Supabase auth flow | Fix | S | Either | — | New account → lands logged in (incl. email-confirm path) | Access
A2 | Auth | Tester sign-up email-confirmation path (auto-confirm or a confirm runbook) | auth · live project needs confirm | Fix | S | Either | A1 | A tester self-confirms or is auto-confirmed; no stuck signups | Access
B1 | Shell | Global nav shell (sidebar + mobile bottom-nav: Brand Coach / Funnel Mapper / Strategy Document) | new shell over App.tsx routes; resolve V1/V2 split enough to reach both | Net-new | M | Matthew | — | Every authed screen has persistent nav; /v2/funnel reachable | Orientation
B2 | Shell | First-run 'start here' landing (two destinations) after first sign-in | new | Net-new | S | Matthew | B1 | Brand-new user lands on it post-signup | Orientation
B3 | Shell | 375px mobile layout fix (coach + funnel usable on a phone) | CSS / layout | Fix | S | Matthew | — | No broken layout at 375px | Orientation
B4 | Coach UI | Single-focus accordion render (one section open; 'needs you (N)' vs auto-managed + managed details) | chapterFields.ts + field model (updated_at, field_source already present) | Reskin | M | Matthew | C1 | Coach renders single-focus over LIVE field data | Core loop
C1 | Coach | Per-field status derivation (needs-you / auto-managed / set) | field model | Net-new | S | Claude | — | Each field gets a UI-consumable status | Core loop
C2 | Coach | Coach alerts: pending-decision ('choose 3 values') + conflict detector ('tagline vs positioning') | new signal over the field model | Net-new | M | Claude | C1 | Alerts strip populated from REAL signals (v1 = simple rules) | Core loop
C3 | Coach | Brand-readiness / grounding computation — SHARED by coach gate, funnel gate, and the 'grounded in' strip | new service (build once) | Net-new | M | Claude | C1 | One service returns readiness consumed in 3 places | Core loop
D1 | Funnel | Callable seam to invoke generate_brief from the app (edge-fn wrapper or app→MCP) | generate_brief (MCP-only today) | Net-new | M | Claude | — | App can call brief generation authenticated | Core loop
D2 | Funnel | Design-brief tab UI (single image / 7-slot set; export / copy) | generate_brief 7-slot image brief | Reskin | M | Matthew+Claude | D1 | Audited stage → brief renders, copyable; claim-gate enforced | Core loop
D3 | Funnel | Prompt tab — thin paste-ready prompt layer (+ send-to Midjourney/DALL·E selector) | new layer over brief slots + generate_concepts | Net-new | S–M | Claude | D1 | A stage → copy-ready prompt grounded in the brand | Core loop
D4 | Funnel | Canvas-degrade fallback (generate from Signature+Avatar when no Canvas yet) | generate_brief / generate_concepts | Net-new | S | Claude | D1 | No Canvas → still a usable, grounded brief; never-fabricate intact | Core loop
D5 | Funnel | Wire the funnel nav link + reorganize the tracker by funnel stage | funnel tracker UI | Reskin | S | Matthew | B1 | Funnel reachable from nav + stage-organized | Core loop
E1 | Strategy | Include the persisted Signature in the exported strategy doc (currently omitted) | MarkdownExportService / generate-brand-strategy-section | Fix | S | Either | — | Exported doc shows the Signature | Core loop
D6 | Funnel | Funnel-as-LOOP: iterate on a funnel artifact, version + organize by avatar / folders (in-flight, agent 7034cdd6) | funnel tracker + brand_assets versions | Net-new | M | Matthew | B1 | User can iterate, save, and revisit funnel-artifact versions | Roadmap
CA1 | Competitor | Competitor Analysis TAB in the prototype: pick competitor brands (Amazon listing / website / storefront / text), select/deselect, compare your brand vs them (IN-FLIGHT, agent 7034cdd6) | prototype: brand-coach-app-prototype.html | Net-new | M | UI agent | — | Tab mocked: configure competitors + brand-vs-competition view | Roadmap
CA2 | Competitor | Promote Competitor Analysis to a 3rd top-level destination (Coach / Funnel / Competitor / Doc) | nav shell (B1) | Net-new | S | Matthew | B1, CA1 | Nav shows the 3rd destination; reachable | Roadmap
CA3 | Competitor | Brand-level 'Competitor Trust Gap Comparison' view (you vs competitors across the 4 IDEA pillars) — today's engine is per-touchpoint | over deployed competitor-analysis-asset engine | Net-new | M | Claude | CA1 | Brand-level 4-pillar comparison renders, grounded (source_refs) | Roadmap
CA4 | Competitor | Pull-seams so Coach + Funnel CONSUME the analysis (not siloed): Coach surfaces competitive-pressure (trust_gap_snapshots feed); Funnel touchpoint pulls competitor insight | trust_gap_snapshots + MCP/coach | Net-new | M | Claude | CA3 | Coach + Funnel both read the competitor analysis | Roadmap
CA5 | Competitor | Ground the tab's connectors in deployed modalities (Amazon listing→DataForSEO, web/storefront→Firecrawl, text→manual); label stubs | _shared/dataforseo.ts / Firecrawl | Net-new | M | Claude | CA3 | Each connector maps to a real modality; unbuilt scopes labeled | Roadmap
CA6 | Competitor | Go-live gates: merge feat/competitor-agents→main, set DATAFORSEO secrets, flag-on, real-ASIN smoke test, counsel review | COMPETITOR_AGENTS_DEPLOY_RUNBOOK | Process | M | Either | CA3 | Competitor surface live + counsel sign-off | Roadmap
F1 | Metrics | New AlphaEventName events on the new surface (see Metrics tab) | src/lib/posthogClient.ts → PostHog 203641 | Net-new | S–M | Claude | — | Events fire to 203641 + visible | Measurable
F2 | Metrics | Extend Product-Health dashboard 759005 with a tester funnel + drop-off view | PostHog dashboard 759005 | Net-new | S | Claude | F1 | Tester funnel + drop-off visible | Measurable
G1 | Deploy | Branch off origin/main; integrate everything; tsc / lint / test green | — | Process | S | Either | all | Clean build off main (NOT feat/alpha-instrumentation) | Safe to ship
G2 | Deploy | Deploy to prod (manual frontend rsync; redeploy MCP if the seam changed) | prod · CI auto-deploy OFF | Process | S | Either | G1 | Live + verified | Safe to ship
G3 | QA | Full-loop QA on the shared account (signup → coach → strategy → funnel brief/prompt) | shared QA account | Process | M | Either | G2 | Loop passes end-to-end on prod | Core loop
G4 | Deploy | Revert the CLAUDE.md DEPLOY-MODE banner before testers onboard | CLAUDE.md | Process | XS | Either | G3 | Banner removed; normal Ask-First gates restored | Safe to ship
G5 | Invite | Send Trevor the 'try it live' note (drafted, never sent) + confirm his web account | Slack / email | Process | S | Matthew | G3 | Trevor + first testers have working accounts + instructions | Invite sent

## Tester Invite Gate
Tester-Invite Gate — what must be true to invite testers
Each gate is a must-be-true; the backlog items that satisfy it are listed. All six green = invite the first testers.
Gate | Must be true | Satisfied by | Why it matters for testers
1 · Access | A tester can sign up, confirm their email, and log in with no blocker. | A1, A2 | If they can't get in, nothing else counts. The friend hit signup/signin bugs — close them first.
2 · Orientation | On first sign-in they immediately understand what to do and can reach both tools. | B1, B2, B3 | The originating problem: 'what is this? what do I do?' A curated first-run + nav fixes it; mobile must work.
3 · Core loop walkable | coach → strategy → funnel → generate a design brief / prompt, end to end on prod. | B4, C1–C3, D1–D5, E1, G3 | This IS the thing we're asking them to test. It must run on real data without a dead end.
4 · Measurable | Tester behaviour + corrective signal are captured. | F1, F2 | We only get learning if drop-offs, field accept/reject/edit, and brief/prompt generation are instrumented.
5 · Safe to ship | Deployed from main, verified, banner reverted, rollback known. | G1, G2, G4 | Deploying from the stale branch would regress prod. Restore Ask-First gates before real users arrive.
6 · Invite sent | Trevor + the first testers have working accounts and clear instructions. | G5 | The self-serve 'try it live' line must be TRUE — accounts confirmed, the loop walkable, instructions in hand.

## Metrics
Metrics — make the tester loop measurable
New AlphaEventName events to fire to PostHog 203641. Plumbing is already live; these are the new events for the new surface.
Event | Fires when | What it answers | New / Exists
nav_destination_changed | User switches Brand Coach ↔ Funnel Mapper ↔ Strategy Doc | Are both destinations discovered + used? Where do they spend time? | New
field_confirmed | User confirms an AI-drafted field | How much of the strategy the AI gets right first time | New
field_edited | User edits / overrides an AI field | The clearest 'the AI got this wrong here' corrective signal (feedback-map P1 gap) | New
value_chosen | User picks their top-N brand values | Completion of a key decision step in the coach | New
coach_alert_shown / _actioned | An alert (conflict / pending decision) is shown / clicked | Do the coach's nudges drive action, or get ignored? | New
funnel_prompt_generated | User generates a paste-ready prompt for a funnel stage | Loop-endpoint usage: are testers actually creating assets? | New
funnel_brief_generated | User generates a design brief (single / 7-slot) | Loop-endpoint usage + which output type they prefer | New
funnel_asset_checked | User checks an existing asset against the brand | Audit usage vs generation usage | New (funnel_* family exists)
signup → first-asset funnel | Dashboard view across the above + existing funnel events | Time-to-first-asset; where testers drop off (the headline metric) | Dashboard 759005

## Roadmap (Deferred)
Roadmap — explicitly NOT this sprint
Value-add deliverables deferred so Sprint 1 stays focused on a walkable, testable core loop.
Deferred item | Why deferred | Pre-req / gate
Full single-focus polish + advanced coach alerts | v1 alerts (simple rules) are enough to test; sophistication is iteration | Tester feedback on v1
In-app asset GENERATION + before/after lift | High value, high lift — likely slips past 6/21; brief/prompt is the honest endpoint now | Loop validated w/ testers
Trevor's Decision-Trigger 'defined workflow w/ advance-criteria' | Bigger build; coach is good-enough to test without it | Matthew + Trevor scope
Brand Defense monitoring (alerts / Buy-Box / listing integrity) | Retention feature; scope after the asset chain is stable (Trevor's 17 Jun brief) | Decision-Trigger lands; Titan get_alerts confirmed
Competitor agents GA (per-touchpoint IDEA-scored) | Engineering done but secrets/process-gated | DataForSEO key + counsel review (ToS / PII)
Multi-avatar end-to-end (CreateAvatarDialog, avatar-scoped sessions) | On a worktree, not main; not required for first testers | Merge + QA
Monetization / paywall / tiers (Free→Starter→Pro→Studio) | Biggest build-gap; Alpha = activated FREE testers first | Verified cost guardrails before paywall
MCP funnel surface (list_touchpoints / upsert / audit as tools) | Gated on the D5 cross-server write-auth decision | D5 resolves
Warehouse auto-pull for test lift | Manual lift entry is fine for Alpha | Ingestion live

## Risks & Dependencies
Risks & dependencies
Watch-items for the 6/21 date
Risk / dependency | Impact | Likelihood | Mitigation
generate_brief requires a Brand Canvas (returns needs_input without one) | A brand-new tester (no Canvas yet) gets a dead end at the loop endpoint | High | D4: degrade to a Signature+Avatar prompt; nudge 'finish your brand for a fuller brief'
generate_brief is MCP-only — no app-callable seam | Funnel UI can't reach it without D1 | High | Build the edge-fn wrapper / app→MCP seam (D1) early; it's on the critical path
New single-focus shell is bigger than 'minimal' | B-items (nav/shell/mobile) are the long pole; risk to 6/21 | Medium | Shell is reskin over built data; cap visible sections; ship nav+landing first, polish later
Auth bug repro is unknown | Can't fix what we can't reproduce; time risk | Medium | Reproduce on prod with the shared account FIRST (A1) before estimating
Conflict detector (C2) is the fuzziest new bit | Over-engineering a smart detector burns the sprint | Medium | v1 = simple deterministic rules (e.g. tagline≠positioning string/field check), not an LLM judge
Deploying from feat/alpha-instrumentation | Would regress prod (branch is 105 behind main) | Low (known) | Branch off origin/main (G1); deploy = manual rsync, CI auto-deploy is OFF
Live project email-confirmation gotcha | Testers get stuck unconfirmed | Medium | A2: auto-confirm or a confirm runbook before invites go out
DEPLOY-MODE banner still lifts Ask-First gates | Risky changes ship unguarded once real users exist | Low | G4: revert the banner before testers onboard (it self-expires 6/21)

## Competitor Analysis (3rd Tab)
Competitor Analysis — the 3rd destination ('Brand vs Competition')
Decision 2026-06-19: its own tab; Coach + Funnel pull from it. Readiness + plan compiled from Trevor's docs, the deployed engine, and the in-flight prototype work.
Aspect | Detail
The decision (6/19) | Competitor Analysis becomes its own top-level destination — 'Brand vs Competition' — focused only on YOUR brand vs competitors. Brand Coach + Funnel Mapper PULL from it. This matches Trevor's intent better than the current funnel-embedded build.
Trevor's stated vision (sources) | • Recommendations_FINAL.docx: 'Competitor Trust Gap Comparison' = a TOP-3 Beta feature; score 'competitor across the four IDEA pillars'. • Brand_Defense_Monitoring_Brief.docx: competitors scored on the SAME Trust Gap lens; 'competitive pressure' = 1 of 3 longitudinal-Trust-Gap feeds. • AVM_DeveloperBriefing_v2.docx: prefers a 'dedicated, named module — an integrated layer, NOT a separate branch' + contextual injection on 'competitor mentions'. • Developer_Brief.docx: 'sections feed data into the Brand Canvas'. • Fathom 6/12 call: 'add competitor URL input; integrate Claude analysis; include in diagnostic'.
Your tab spec (to agent 7034cdd6) | Configure which brands to compare — connect Amazon listings, websites, Amazon storefronts, or a text description; easily select/deselect competitor brands; the tab focuses only on your brand vs the competition.
What's BUILT (engine) | competitor-analysis-asset (IDEA-scored, Sonnet 4.6, grounding gate with source_refs) + brand-defense-monitor — BOTH deployed ACTIVE in prod (from the feat/competitor-agents worktree, 63 behind main). 3 of 7 modalities wired (DataForSEO listing, Firecrawl web/storefront, reviews VoC). 5 migrations + funnel UI panels, behind flag VITE_COMPETITOR_AGENTS (default OFF).
What's NEW for the tab | (1) A BRAND-LEVEL 'you vs competitors across the 4 pillars' view — today's engine is per-touchpoint. (2) The 3rd-destination nav. (3) Pull-seams so Coach (via the trust_gap_snapshots competitive-pressure feed) + Funnel consume it.
In-flight NOW (other agents) | Session 7034cdd6 = building the tab in brand-coach-app-prototype.html + funnel-as-loop (UI/design). Session f0860233 = competitor backend / merge-to-main / MCP redeploy.
Go-live gates | Merge worktree → main · set DATAFORSEO_USERNAME/_PASSWORD · flag-on + rebuild/rsync · real-ASIN smoke test (grounding gate) · counsel review (Amazon ToS / reviewer PII) · Brand Defense stays STUBBED until Titan get_alerts coverage is verified.
This week vs roadmap | NOT a tester-invite gate. THIS WEEK = the PROTOTYPE/design of the tab only. The wired feature (brand-level view + pull-seams + flag-on + counsel) = next-sprint roadmap. Optional tester WOW: light up the EXISTING funnel competitor panels behind the flag IF counsel is comfortable.