## Brand-Coach MCP Status
Component | Status | Current State Notes | Next Goal | Goal Prompt | Workflow Prompt | On Critical Path?
Brand-coach MCP host / gateway (TS streamable-HTTP, dependency root) | Testing | SHIPPED (branch feat/brand-coach-mcp-host): TS streamable-HTTP gateway under src/mcp/ (three-layer service->tool/register->server). Tools: health + STABLE IV-OS reads list_assets/get_asset via IvosLedgerClient (graceful when IV-OS unreachable/empty). Per-request Supabase-JWT identity via AsyncLocalStorage (no cross-request bleed); SERVER_INSTRUCTIONS guard; MF-5 redaction logger. Verified: typecheck:mcp clean, eslint clean, 11/11 vitest green, live boot (GET /healthz 200, MCP initialize, tools/call health). Deps: @modelcontextprotocol/sdk ^1.29 + tsx. Uncommitted (no auto-commit). | Pre-exposure hardening (CORS, rate-limit, per-tool authz) + wire a live IVOS_MCP_URL once IV-OS deploys; otherwise complete -> proceed to the first owned asset-chain tool. | Create a minimal TypeScript MCP gateway (official MCP SDK, streamable-HTTP) under src/mcp/ mirroring the IV-OS sibling package's three-layer structure (service fn -> tool file/register() -> server registration). Implement a health tool + SERVER_INSTRUCTIONS guard. Bind caller identity from the Supabase JWT (never from the wire) into an AsyncLocalStorage scope reset in finally. Add a thin ivos-client adapter calling the CANONICAL IV-OS marketing MCP server-to-server, binding ONLY the STABLE reads list_assets + get_asset; reference all not-yet-bound IV-OS tools by capability (do not pin signatures). Ship the MF-5 log-redaction contract test. Mirror the IV-OS package format (OVERVIEW + PLANNING + STATUS). | Use a workflow: Agent A reads the IV-OS sibling package (iv-os-mcp-planning/) + Inventory Hero MCP + skills 040/041 and drafts the host scaffold; agent B wires the IV-OS-client adapter and a contract test that the STABLE reads round-trip (expect ledger-empty until IV-OS writes populate content_agents.db); agent C adds the identity-binding + reset-in-finally test and the MF-5 log-redaction contract test. | Y
generate_concepts (concept — first chain link) | Testing | SHIPPED 2026-06-03: composes idea-framework-consultant-claude verbatim via EdgeFnClient (identity-forwarded JWT), strict-JSON + numbered-list fallback parser, JWT-gated with graceful anonymous denial. Canon grounding still by-capability (IV-OS canon reads Not Started upstream). Tests green. | Wire auto-recording (log_asset) + canon grounding when IV-OS canon reads ship. | Implement generate_concepts on the host's three-layer pattern. Compose callConsultant (idea-framework-consultant-claude) to produce concept candidates from avatar_id/channel/brief. READ IV-OS get_brand_voice/get_positioning/get_messaging_pillars by capability behind the adapter (PROVISIONAL — stub/skip gracefully if unbound). Return candidates; do NOT build a local concept store. Wire the log_asset write behind a capability flag so the chain produces now and records when D5 lands. | Use a workflow: Agent A wires the callConsultant composition + canon reads; agent B writes tests that concepts generate WITHOUT an IV-OS write binding (proving the owned chain ships independent of IV-OS writes); agent C adds the deferred log_asset capability hook + test. | Y
publish_filter_check (publish_filter — compliance gate) | Testing | SHIPPED 2026-06-03 — D6 DECIDED (deterministic rule-based v1, documented in service/publishFilter.ts): medical claims fail; superlatives/urgency/environmental warn; channel length caps; shouting ratio; verdict pass¦warn¦fail + per-violation fix hints. Pure (anonymous-safe). IV-OS get_safe_claims/canon grading activates by capability. Tests green. UPDATE 2026-06-04: assessment auto-recording wired (record_assessment via request_id, verdict mapped, opt-out, never-fail). | Add IV-OS safe-claims/canon grading when those reads ship; consider LLM-graded v2 if operator wants. | After D6 is decided, implement publish_filter_check: take content + avatar_id, validate claims STRICTLY against IV-OS get_safe_claims (capability ref, not a local allowlist) + canon rules, return verdict + violations. On pass, call update_asset_status by capability (ADR 0001 approval lifecycle). If the verdict is Trevor-voiced, gate on R-015. Do NOT reinvent scoring if D6 aligns to the IV-OS 150-point assessment. Keep within F-054/055/063; respect F-056 image-gen NON-GOAL. | Use a workflow: Agent A drafts the D6 decision memo (net-new scorer vs IV-OS read, with F-054/055/063 + F-056 boundaries) for Matthew+Trevor; agent B implements the chosen path with a fixture set of compliant/non-compliant claims; agent C adds the get_safe_claims capability binding + violation tests. | Y
draft_asset (asset_draft — produces copy asset) | Testing | SHIPPED 2026-06-03: verbatim wrap of brand-copy-generator (CopyRequest mirrored 1:1, Calculation Parity; engine grounds in caller's KB server-side and forwards user JWT per PR #2). Returns copy+format. Tests green. UPDATE 2026-06-04: auto-recording wired (log_asset, opt-out, never-fail). | Wire auto-recording via log_asset (chain auto-recording slice). | Implement draft_asset wrapping brand-copy-generator VERBATIM (Calculation Parity). Inputs concept_id/format/avatar_id; READ IV-OS canon (get_brand_voice/get_positioning) + product (get_product_by_asin/get_safe_claims) by capability so the IV-asset path uses canonical IV voice, not the user profile. Return copy + alternates; route persistence through IV-OS log_asset (capability flag) — never a local asset store. | Use a workflow: Agent A wraps brand-copy-generator + wires canon/product reads; agent B writes a parity test (MCP draft byte-identical to the edge-fn output for fixed inputs); agent C adds the log_asset capability hook + the IV-voice-not-user-voice assertion. | Y
design_test (test_design — final chain link) | Testing | SHIPPED 2026-06-03: pure composer — lettered variants, even traffic split, channel-mapped primary metric, min-sample + stopping rule. record_test NOT yet bound at gateway (IV-OS tool + ab_tests store exist upstream). Tests green. | Bind record_test at the gateway and wire auto-recording of designed tests. | Implement design_test: take hypothesis + asset_ids[] + variants, compose drafted alternates into an A/B test spec, and call IV-OS record_test by capability (asset_ids link to log_asset request_ids). Do NOT build a brand-coach test store (IV-OS ab_tests/ab_test_variants already ship). Gate the record_test binding on the brand-coach-side D5 transport/auth decision; until then return the designed test spec locally. | Use a workflow: Agent A designs the variant-composition logic + spec shape; agent B writes tests that a test designs WITHOUT a record_test binding; agent C adds the record_test capability hook to bind when D5 lands. | Y
IV-OS consumption client (server-to-server MCP client adapter) | Testing | SHIPPED 2026-06-03 (iteration 2, parallel session) — D5 RESOLVED: writes identity-gated at THIS gateway (tools/writeAuth.ts; actor=brand-coach-mcp:<userTag>); log_asset/update_asset_status/record_assessment + get_asset_history bound; LIVE cross-server round trip verified vs real IV-OS (log->in_review->assessment->history). Known limitation: STABLE reads parse empty vs live IV-OS (Markdown-only) — upstream reads-structured-output slice. | Bind the two STABLE reads now behind a thin capability adapter; reference the STABLE-IN-TESTING writes + PROVISIONAL knowledge reads by capability; bind the writes when D5 lands. | Build a thin IV-OS-client adapter that calls the CANONICAL IV-OS marketing MCP (NOT the stale clone). Bind list_assets + get_asset (STABLE) with a contract test tolerating ledger-empty. Expose write-produced-asset / record-test / read-canon / read-product / read-funnel as capability stubs; the write capabilities map to BUILT IV-OS tools (log_asset/update_asset_status/record_test/get_test_result) and bind once D5 (service-account vs token-passthrough) is decided. Reference by capability; do not pin signatures (ADR 0001 made update_asset_status an approval-lifecycle write). | Use a workflow: Agent A points the adapter at the canonical repo + binds the STABLE reads with a round-trip test; agent B drafts the D5 transport/auth decision memo (brand-coach-side); agent C builds the capability-stub layer + a bind test harness for the BUILT IV-OS write tools once D5 lands. | Y
Chain auto-recording (produce -> record in one call) | Testing | SHIPPED 2026-06-04: draft_asset auto-records via ivos.logAsset (content_type=format, actor brand-coach-mcp:<userTag>, status=success, optional campaign_id); publish_filter_check records via ivos.recordAssessment when request_id supplied (verdict map warn->needs_work, summary+recommendations from violations). record:boolean=true opt-out on both; writes identity-gated (anonymous: check runs, recording denied with note); NEVER-FAIL (degraded write annotates structuredContent.recorded). Gateway-only controls stripped before the engine call (parity preserved). 6 dedicated tests; 39/39 suite green. | Extend to design_test once record_test binds at the gateway. | Add auto-recording to the owned chain tools: after a successful draft_asset, call ivos.logAsset with the produced copy (content_type=format, agent_name=brand-coach-mcp:<userTag>); after publish_filter_check on a known request_id, call ivos.recordAssessment with verdict+violations; add record:boolean=true input to opt out; never fail the tool if the write degrades (note it in structuredContent). Tests: stub IvosLedgerClient, assert write called with attributed actor + graceful degradation. | Use a workflow: agent 1 wires draft_asset->log_asset + opt-out flag; agent 2 wires publish_filter_check->record_assessment; agent 3 (verify) stubs the ledger client and adversarially checks attribution, opt-out, and never-fail semantics; finalize updates STATUS/OVERVIEW. | Y
run_trust_gap (diagnostic — convenience) | Testing | SHIPPED 2026-06-03: in-process wrap of src/lib/trustGap.ts buildTrustGap — literal Calculation Parity (parity test asserts byte-identical output to the in-app engine). | None — complete pending live QA. | Implement run_trust_gap on the host pattern, calling trustGap.ts:buildTrustGap IN-PROCESS (no edge-fn hop, no duplicate scorer). Inputs diagnostic_id OR scores; outputs scores/bands/gap. Add a parity test asserting byte-identical output to the app code path. | Use a workflow: Single agent — wrap the pure scorer, add a parity test against a fixed fixture, register the tool. | N
run_diagnostic (diagnostic — convenience) | Not Started | Engine EXISTS: SupabaseDiagnosticService (calculateScores + saveDiagnostic) + diagnostic-interpretation edge fn. SECURITY C1: config.toml L76-77 sets verify_jwt=false; the fn body is scores-only/body-driven with NO getUser/auth and NO DB read (works for guests). UPDATE 2026-06-03: C1 abuse controls (keep-public + origin allowlist + body cap + rate limit) FIXED in PR #3 — wrap unblocked once merged. | Wrap the 6-question flow + interpretation, binding caller identity BEFORE the interpretation leg. | Implement run_diagnostic wrapping calculateScores + saveDiagnostic + diagnostic-interpretation. CRITICAL: bind caller identity in the gateway BEFORE invoking the public interpretation edge fn (it enforces none). Persist the submission user-scoped. Add a test that an unbound caller is rejected at the gateway. | Use a workflow: Agent A wraps the flow; agent B adds the identity-binding-before-interpretation test (C1 mitigation). | N
generate_signature (diagnostic — convenience) | Not Started | Engine EXISTS: reveal-signature edge fn (frozen no-parroting prompt, index.ts L81). Accepts conversation[] OR fields OR reviews and declines gracefully if all empty (does NOT strictly require conversation). PERSISTENCE MISSING: no signatures table/column (verified). D2 OPEN: conversation-first headless turn vs synthesize-context-bundle (latter brushes the locked no-parroting input rule -> R-015). | Decide D2, then pass-through reveal-signature; route any save through IV-OS log_asset (no local store). | After D2 is decided, implement generate_signature as a pass-through to reveal-signature. If context-bundle synthesis is chosen, gate on R-015 (it brushes the locked no-parroting input rule). The conversation-first path (D2 resolution (a)) can use a run_conversation headless transcript. Persist a chosen Signature via IV-OS log_asset (capability; ADR 0001 maps it to a ContentHistory row, content_type likely 'other') — do NOT add a brand-coach signatures table. | Use a workflow: Agent A drafts the D2 decision memo for Trevor; agent B implements the chosen path verbatim + a no-parroting guard test. | N
build_avatar (diagnostic — convenience; subsumes get_avatar/update_avatar_field/toggle_field_lock) | Not Started | Engine EXISTS: SupabaseAvatarService + FieldPersistenceService (manual-edit-lock, toggleFieldLock at :193). SUBSUMES the prior packet's get_avatar/update_avatar_field/toggle_field_lock. SECURITY MF-2: lock is TS-only (FieldPersistenceService.ts:52 is the only gate); migration has is_locked BOOLEAN DEFAULT false + a set_timestamp trigger only — NO trigger forbidding AI writes from clearing is_locked. field_source must be server-set, never trusted from MCP args (confused-deputy vector). UPDATE 2026-06-03: MF-2 lock DB trigger shipped in PR #2 — wrap unblocked once merged. | Wrap avatar/field read+write+lock-toggle in-process; ship the MF-2 DB trigger with this first write tool. | Implement build_avatar wrapping SupabaseAvatarService + FieldPersistenceService IN-PROCESS (parity-critical lock gate), subsuming get_avatar/update_avatar_field/toggle_field_lock. Server-set field_source; never trust it from MCP args. Ship the MF-2 DB trigger forbidding AI-source writes from clearing is_locked, in the same change. Add a test that an AI-source upsert cannot clear a locked field via either the TS path or direct SQL. | Use a workflow: Agent A wraps the services in-process; agent B writes + applies the MF-2 DB trigger migration; agent C adds the bypass-attempt test (TS + direct SQL). | N
search_user_kb (diagnostic — convenience) | Not Started | Engine EXISTS: match_document_chunks RPC (migration 20260406000000_pgvector_rag_migration.sql L53-93, pgvector ada-1536). SECURITY MF-1: SECURITY DEFINER, filters WHERE ukc.user_id = match_user_id with NO auth.uid() caller check, GRANT EXECUTE TO authenticated (confused deputy — any authenticated principal can read any owner's KB). UPDATE 2026-06-03: MF-1 confused-deputy hardened (auth.uid() guard, 4 RPCs) in PR #2 — wrap unblocked once merged. | Wrap the RPC; harden MF-1 inside the function before exposing. | Implement search_user_kb wrapping match_document_chunks. Before exposing, harden MF-1: verify inside the function that the caller is authorized (owns the id OR has an active va_grants row). Add a test that caller A cannot read caller B's KB. | Use a workflow: Agent A applies the MF-1 hardening migration; agent B wraps the RPC + adds the cross-owner denial test. | N
run_conversation / continue_conversation (conversation — convenience) | Not Started | Engine EXISTS: idea-framework-consultant-claude via callConsultant (SupabaseChatService.ts + chat/ChatEdgeFunctionService.ts:115) — the literal Trevor-coaching core and chat-primary surface backend. Prior packet tools 11/12 (re-surfaced here, not dropped). Caveats: MCP is request/response so the streamed text_delta/extracted_fields must be buffered into one assembled reply; history is threaded server-side (no previous_response_id). | Wrap the coach turn verbatim, buffering streamed deltas into one assembled reply; extracted fields still persist through the FieldPersistenceService lock gate. | Implement run_conversation/continue_conversation wrapping idea-framework-consultant-claude via callConsultant VERBATIM. Buffer the streamed text_delta + extracted_fields and emit ONE assembled reply (Q5 ack, not a voice change). Persist extracted fields through FieldPersistenceService (the lock gate). Expose the turn as a candidate headless transcript for generate_signature (D2 resolution (a)). Do NOT route chat through the MCP for the primary owner surface (D3 confirm-only). | Use a workflow: Agent A wraps callConsultant + the delta-buffering; agent B adds a test that a multi-turn exchange threads server-side and extracted fields hit the lock gate; agent C wires the headless-transcript handoff to generate_signature. | N
export_strategy_doc (export — convenience) | Not Started | Engines EXIST: generate-brand-strategy-document / -section / -pdf (all three present in supabase/functions/). Prior packet tool 18 (re-surfaced here, not dropped). Terminal 'doing' output the owner expects; LLM-gen, idempotent per snapshot. | Wrap the three strategy-doc edge fns verbatim; decide whether the produced doc routes through IV-OS log_asset (it is an asset) or stays a brand-coach read. | Implement export_strategy_doc wrapping generate-brand-strategy-document/-section/-pdf VERBATIM (Calculation Parity). Decide whether the produced doc also routes through IV-OS log_asset (consistent with the Signature-via-log_asset stance) or stays a read. Do NOT build a brand-coach doc store if it routes to IV-OS. | Use a workflow: Agent A wraps the three edge fns; agent B adds a parity test + the log_asset-vs-read routing decision note. | N
Cross-cutting: path-repoint to canonical IV-OS | Done | DONE 2026-06-03: repo files were already grep-clean; stale memory pointer (project_mcp_surface_reframe L20) repointed to canonical with a re-run-graphify caveat; project_graphify_corpus is about THIS repo's graph (no stale path). | Re-run graphify against canonical IV-OS when its graph is next needed. | Repoint memory entries project_mcp_surface_reframe.md (L20) and project_graphify_corpus.md to the canonical IV-OS path /Users/matthewkerns/workspace/ecommerce/ecommerce-brand-business-os, using project_ivos_brandcoach_mcp_boundary.md as the anchor. Re-run graphify against canonical so IV-OS graph queries are not built from the stale tree. | Use a workflow: Single agent — edit the two memory entries, re-run graphify against canonical, verify a sample IV-OS query resolves against canonical paths. | N
Reference: prior design packet (do-not-re-derive) | Done | /tmp/_mcp_inspect/prior_packet (00_SUMMARY..05_open_questions + reference-detail). Provides the 19-tool design, transport/state model, auth/scoping, lock preservation, chat recommendation, phased build, and the 6 open decisions. Reference; do NOT re-derive its strategy. | Reference only — pull design + open decisions; do not re-design. | Reference the prior packet for any design detail (tool inventory, transport, VA model, the 6 decisions). Do not re-derive; cite section numbers (e.g. 03 §0/§2 for the TS-gateway rationale, 03 §1 for the dropped/folded tool delta, 05 §6 for the must-fixes). | N/A - reference artifact, not a build target. | N
Reference: IV-OS marketing MCP (upstream dependency) | In Progress | Canonical /Users/matthewkerns/workspace/ecommerce/ecommerce-brand-business-os, iv-os-mcp-planning package dated 2026-06-02. CORRECTION vs the task preamble: ALL FIVE critical-path components are BUILT — host, asset-ledger read (list_assets/get_asset), asset-ledger write (log_asset/update_asset_status), store-of-record ADR 0001 (DONE — single-tenant/no-auth, no migration needed), and the A/B Test Ledger (durable ab_tests/ab_test_variants tables + add_ab_tests.py migration, record_test/list_tests/get_test_result with two-proportion-z significance). All at status Testing, 56/56 green (not 19/19), on branch feat/iv-os-marketing-mcp-asset-ledger. Tool files verified present. Knowledge reads (canon/product/funnel) Not Started. The 'no durable test store' and 'ADR pending' blockers are RESOLVED. UPDATE 2026-06-03: IV-OS shipped record_assessment/get_asset_history/include_full_content; reads-structured-output is a later upstream slice. | Track the IV-OS merge/deploy + the knowledge-read builds; bind brand-coach write capabilities once the brand-coach-side D5 auth decision lands (the IV-OS tools themselves are ready). UNKNOWN: content_agents.db empty until populated. | Reference the IV-OS sibling package (OVERVIEW/PLANNING/STATUS). Bind the STABLE reads now; treat the BUILT write tools as STABLE-IN-TESTING (bind on the brand-coach-side D5 decision, pre-merge/pre-deploy caveat); treat knowledge reads as PROVISIONAL until they ship. Do not duplicate the ledger or knowledge. | N/A - upstream dependency tracked via the IV-OS-client adapter capability layer. | Y

## Legend
Brand-Coach Marketing MCP - Status Workbook
Generated | 2026-06-04
Canonical repo | /Users/matthewkerns/workspace/ecommerce/ecommerce-brand-business-os (branch main; working tree on feat/iv-os-marketing-mcp-asset-ledger). NEVER the stale clone at ecommerce-tools/brand-systems/ecommerce-brand-business-os (~5 days behind, no content-engine packages).
Upstream dependency | IV-OS Marketing MCP (Python FastMCP, canonical repo). VERIFIED 2026-06-02: all five critical-path components built + in Testing (56/56 green) on feat/iv-os-marketing-mcp-asset-ledger — host, asset read (list_assets/get_asset STABLE), asset write (log_asset/update_asset_status), store-of-record ADR 0001 (single-tenant/no-auth, DONE), and durable A/B test ledger (ab_tests/ab_test_variants + add_ab_tests.py, record_test/list_tests/get_test_result with two-proportion-z significance). Write tools re-flagged STABLE-IN-TESTING (pre-merge/pre-deploy; gated only by the brand-coach-side D5 auth decision, NOT IV-OS readiness). Knowledge reads (brand canon, product truth, funnel) still Not Started IV-OS-side = the genuine PROVISIONAL surfaces. Reference consumed tools BY CAPABILITY; do not pin signatures (ADR 0001 made update_asset_status drive a ContentReview approval lifecycle). UNKNOWN: live content_agents.db empty until writes populate it.
On Critical Path = Y | On Critical Path = Y ONLY for components that directly PRODUCE or TEST a marketing asset: the OWNED concept -> publish-filter -> draft -> test-design chain PLUS the consumed log_asset / record_test writes, plus the two infra substrates (host + IV-OS client) the chain runs on. Diagnostics (Trust Gap, Signature, avatar, KB), conversation, export, and all knowledge reads are CONVENIENCE (N) — they inform the chain but do not produce an asset.
BUILD TARGET (yellow row) | search_user_kb is highlighted as the FIRST post-merge build (lowest-effort wrap once PR #2 lands the MF-1 auth.uid() guard). Nothing is buildable before those merges; all critical-path components are Testing.
On Critical Path (peach rows) | Rows that directly produce or test a marketing asset.
Status values | Not Started / In Progress / Testing / Done
Next Goal | GATED on operator actions: merge PR #2 (MF-1+MF-2) then wrap search_user_kb + build_avatar; merge PR #3 (C1) then wrap run_diagnostic; decide D2 for generate_signature. No unblocked in-repo critical-path work remains — every Y component is Testing.
Note | 'Status' reflects the MCP TOOL/component, not the data/engine behind it.