## Summary
Summary — feature readiness by launch phase
Live rollup from the Features sheet. Status column derives on-track / at-risk / blocked from the underlying data.
phase | features_required | complete | in_progress | blocked | not_started | percent_complete | status
Alpha
Beta
GA
Post-GA
Earliest blocker (first feature with status = blocked)

## Problems
Problems — the grand-vision list, mapped to features
Each problem is mapped to the features that help solve it. fulfilment_status derives from the status of mapped features. alpha_testable = whether Alpha-stage features alone are enough to validate this problem with testers.
problem_id | problem_statement | earliest_phase_solvable | alpha_testable | mapped_features | feature_count | complete_or_review_count | fulfilment_status | notes
P-001 | Generic AI doesn't know my customer deeply enough. | Alpha | Yes | F-004,F-005,F-006,F-007,F-008,F-009,F-012,F-022,F-058,F-060 | 10 |  |  | Core Alpha thesis: Avatar Builder + Forensic Canvas produce a depth of customer understanding generic prompting can't reach. F-022 (Coach mode) extends this in Beta. GEN3 (2026-05-25): = cannot articulate what the customer is actually buying → The Signature (F-060) is the answer; the Decision Trigger (F-058) sharpens it. MVP-critical, validate first. Free tier.
P-002 | I don't know what to ask myself about my customer. | Alpha | Yes | F-001,F-004,F-005,F-006,F-007,F-009,F-060,F-061,F-062 | 9 |  |  | 10-Q conversation + 4 Avatar Builder sections provide the inquiry structure. F-009 'Think About This' mode explicitly generates reflective questions per field.
P-003 | My brand strategy doc is shallow or doesn't exist. | Alpha | Partial | F-003,F-008,F-023,F-053 | 4 |  |  | F-008 (Forensic Canvas via generate-brand-strategy-document) is the primary fulfilment — substantially shipped. Polished Word export (F-023) and multi-angle (F-053) are Beta extensions.
P-004 | My copy and creative aren't grounded in strategy. | Beta | No | F-008,F-020,F-021,F-055 | 4 |  |  | Requires Create mode outputs (F-020 Amazon, F-021 Voice Guide, F-055 Design brief). None ship in Alpha. The canvas (F-008) is the anchor but not the deliverable for this problem.
P-005 | My customer's actual language doesn't make it into my copy. | Beta | Partial | F-007,F-008,F-020,F-021,F-063 | 5 |  |  | F-007 Voice of Customer extracts verbatim language in Alpha. F-020/F-021 (Beta) consume it. Alpha can prove 'we capture the language'; only Beta proves 'it shows up in your copy'.
P-006 | My existing image/video set is doing something — but I can't tell what's missing or off. | GA | No | F-006,F-007,F-054,F-055 | 4 |  |  | InfinityVault's specific need (N-002). F-054 is conditional on the asset-tracking decision gate. F-006/F-007 supply the 'what should this connect to' context.
P-007 | I have no thinking partner who remembers my brand. | Beta | No | F-022,F-031,F-049 | 3 |  |  | F-022 Coach mode is the answer. RAG (F-049) makes the memory queryable. F-031 (My Brands) lets the partner know which brand we're discussing.
P-008 | I can't cheaply test multiple positioning angles. | Beta | No | F-042,F-053,F-055 | 3 |  |  | F-053 is the primary fulfilment. F-055 lets each angle drive its own design brief. F-042 comparison view (GA) lets the user A/B them.
P-009 | I can't tell when my strategy and my live assets have drifted apart. | GA | No | F-028,F-029,F-030,F-043,F-054 | 5 |  |  | Conditional on the asset-tracking decision. F-043 field edit history adds the temporal dimension on the strategy side.
P-010 | Every marketing decision feels reactive. | GA | No | F-008,F-022,F-038,F-053 | 4 |  |  | Forensic Canvas as North Star (F-008), Coach for ongoing decisions (F-022), performance metrics (F-038) close the loop. F-053 lets decisions live at the angle level.
P-011 | I don't know where my brand is failing. | Alpha | Yes | F-057,F-059,F-027 | 3 |  |  | GEN3 (2026-05-25): Trevor's problem #3/#9 — the Trust Gap™ Score (F-057) names the gap (insight / positioning / empathy / authenticity) and the bridge (F-059) turns it into momentum. MVP-critical: this is the hook, validate FIRST [Analysis 2026-05-17]. Free tier.
P-012 | Brand strategy expertise is inaccessible at my price point. | Beta | No | F-019,F-064 | 2 |  |  | GEN3 (2026-05-25): Trevor's problem #7 — a brand strategist costs £3k–£15k; the freemium app (F-019) delivers structured brand thinking at £29/mo, with locked-but-visible fields (F-064) enticing upgrade. Paid tier.

## Features
Features — implementation status by launch phase
feature_id | feature_name | area | description | phase_required | priority | status | percent_complete | blocker | owner | depends_on | problems_addressed | effort_estimate_hours | actual_hours | notes | last_updated
F-001 | Layer 1 conversation engine | conversation | 10-question Layer 1 flow with Trevor-voice fallback responses and real-time canvas-sidebar updates. | Alpha | P0 | in_progress | 35 |  | Matthew | F-018 | P-002 | 40 | 0 | AUDIT 2026-05-16: Trevor persona prompt + free-form Claude streaming exist; the *10-question script* and per-question off-topic fallbacks DO NOT (F-001.1/F-001.2). Streaming + persistence are solid. Mobile keyboard handling minimal. | 2026-05-25
F-002 | Canvas sidebar real-time population | canvas | Canvas sidebar updates as Layer 1 conversation progresses, showing extracted fields with confidence indicators. | Alpha | P0 | in_progress | 65 |  | Matthew | F-001,F-012 |  | 20 | 0 | AUDIT 2026-05-16: Field-extraction → sidebar pipeline is mature (F-002.1, 80%). Quality badges render BUT use value heuristics (fieldQualityScore) not extractor confidence — acceptance criterion not literally met (F-002.2 reduced from 100→75). Mobile sheet works but state not persisted (F-002.3). | 2026-05-25
F-003 | Draft Canvas synthesis | canvas | Synthesise Layer 1 inputs into a coherent Draft Canvas with DRAFT badge and clear Forensic upgrade prompt. | Alpha | P0 | in_progress | 14 |  | Matthew | F-001,F-018 | P-003 | 24 | 0 | AUDIT 2026-05-16: Tier distinction is conceptual only — zero structural code hits for 'DRAFT'/'tier'. Synthesis with Trevor voice exists (generate-brand-strategy-section + voice.ts) but generates the full doc, not a Draft subset. DRAFT badge and Forensic upgrade CTA both 0%. | 2026-05-25
F-004 | Avatar Builder — Psychographic Profile | avatar_builder | Section 1 of the four-section Avatar Builder. Captures values, identity, worldview. | Alpha | P0 | in_progress | 62 |  | Matthew | F-003,F-009 | P-001,P-002 | 32 | 0 | AUDIT 2026-05-16: V2 chapter UI delivers progressive disclosure + persistence well, but field schema flattens Gen 3 psychographic dimensions into coarse textareas (F-004.1 60%). 3 of 4 AI modes present; FieldChatButton missing from V2 (F-004.3 35%). Completion gate logic exists but button not mounted in render tree (F-004.5 55%). RECONCILE (2026-05-25): maps into the new 5-stage conversational flow ending in The Signature (F-060); guided dialogue, not a 4-section form [F 144128256 @04:26]. 5-stage structure pending Trevor/Matthew sign-off. | 2026-05-25
F-005 | Avatar Builder — Buying Behaviour | avatar_builder | Section 2. Captures purchase triggers, objections, decision criteria, channels. | Alpha | P0 | in_progress | 55 |  | Matthew | F-004 | P-001,P-002 | 32 | 0 | AUDIT 2026-05-16: V2 chapter map has no dedicated 'Buying Behaviour' chapter — closest is BUYER_INTENT which is conceptually different. V1 AvatarBuilder has the right tab. Data shape exists; UI split V1↔V2. RECONCILE (2026-05-25): maps into the new 5-stage conversational flow ending in The Signature (F-060); guided dialogue, not a 4-section form [F 144128256 @04:26]. 5-stage structure pending Trevor/Matthew sign-off. | 2026-05-25
F-006 | Avatar Builder — Emotional Journey Mapping | avatar_builder | Section 3. Pre/during/post purchase emotional states; The Decision Trigger™ originates here (captured standalone in F-058). | Alpha | P0 | in_progress | 43 |  | Matthew | F-005 | P-001,P-002,P-006 | 36 | 0 | AUDIT 2026-05-16: Emotional fields exist (EMOTIONAL_CONNECTION + CUSTOMER_EXPERIENCE chapters) but Gen 3 Emotional Journey framing absent; Trigger Moment field with elevated visual treatment (F-006.2) is the most prominent miss — zero hits in codebase. RECONCILE (2026-05-25): maps into the new 5-stage conversational flow ending in The Signature (F-060); guided dialogue, not a 4-section form [F 144128256 @04:26]. 5-stage structure pending Trevor/Matthew sign-off. | 2026-05-25
F-007 | Avatar Builder — Voice of Customer | avatar_builder | Section 4. Paste-in reviews and testimonials; extract verbatim language for copy hooks. | Alpha | P0 | in_progress | 30 |  | Matthew | F-006 | P-001,P-002,P-005,P-006 | 40 | 0 | AUDIT 2026-05-16: Review intake is URL/ASIN-driven via ReviewAnalyzerModal (scrape model), not Gen 3 paste-raw-reviews model. voice-of-customer-analysis edge function DOES NOT EXIST. V1 analysis is fully mocked. Use/discard phrase cards (F-007.3) ~10%. RECONCILE (2026-05-25): maps into the new 5-stage conversational flow ending in The Signature (F-060); guided dialogue, not a 4-section form [F 144128256 @04:26]. 5-stage structure pending Trevor/Matthew sign-off. | 2026-05-25
F-008 | Forensic Canvas synthesis | canvas | 28+ field canvas synthesised from Avatar Builder, auto-populating from Avatar data partially in real time; strategy doc generable at any point (no forced step-gating). The Decision Trigger™ displayed prominently. | Alpha | P0 | in_progress | 39 |  | Matthew | F-004,F-005,F-006,F-007 | P-001,P-003,P-004,P-005,P-010 | 40 | 0 | AUDIT 2026-05-16: 35-field schema exists (exceeds 28+) and Markdown export pipeline is mature, but Forensic *tier* differentiation does NOT exist — single unified synthesis path. Trigger Moment 'Strategic Entry Point' callout (F-008.3) and Draft↔Forensic toggle (F-008.4) both 0%. Rollup dropped from 80→39%: the doc ships, but the criteria asking for tier-specific behaviour are unmet. GEN3 (2026-05-25): canvas auto-populates from Avatar data (partially real-time); no forced step-gating; 'Trigger Moment' renamed The Decision Trigger™ (also captured standalone in F-058) [F 144128256 @27:00,@31:00]. | 2026-05-25
F-009 | AI Assistance system | avatar_builder | Four modes — Think About This, Real-World Examples, Get AI Suggestions, Get AI Auto-Populate — available per field. | Alpha | P0 | in_progress | 19 |  | Matthew | F-018 | P-001,P-002 | 48 | 0 | AUDIT 2026-05-16: Only ONE AI mode is independently invocable — a single 'Generate with AI' button per field (AIButton.tsx). 'Think About This' and 'Real-World Examples' modes don't exist; 'Auto-Populate' is delivered implicitly via chat extraction + ghost text. No 4-mode selector UI. Rollup dropped from 30→19%. GEN3 (2026-05-25): MVP ships static example text for avatar/Before-State prompts; AI-suggestion path deferred and paid-tier when built [F 144128256 @11:42-12:52]. | 2026-05-25
F-010 | Progressive disclosure UI | design_system | Avatar Builder fields reveal progressively to avoid form fatigue; mobile-first. | Alpha | P0 | not_started | 2 |  | Matthew |  |  | 24 | 0 | AUDIT 2026-05-16: shadcn Accordion used informally for chapter disclosure; no documented disclosure pattern, no mobile-first audit committed. Rollup dropped from 25→3%. | 2026-05-25
F-011 | Manual edit lock | avatar_builder | Fields manually edited by the user are flagged and never silently overwritten by AI suggestions. | Alpha | P0 | in_progress | 57 |  | Matthew |  |  | 12 | 0 | AUDIT 2026-05-16: field_source ('ai'¦'manual') exists and survives reload BUT is not the same as a 'manuallyEdited' boolean — system pairs it with separate is_locked user-toggle. AI overwrite guard works only for *explicitly locked* fields (F-011.2 65%), not for manually edited unlocked ones. F-011.1 reduced from 100→70% in_review. | 2026-05-25
F-012 | Field extraction pipeline with confidence scoring | infrastructure | Conversation inputs → structured field extraction with per-field confidence score. Drives the quality badges. | Alpha | P0 | in_progress | 45 |  | Matthew |  | P-001 | 32 | 0 | AUDIT 2026-05-16: Edge function returns confidence scores (F-012.1 85%), but no confidence→badge mapping is implemented (F-012.2 was 100% wrongly — now 50%). Two unrelated badge systems coexist (heuristic on sidebar, percentage on chat). | 2026-05-25
F-013 | Feedback Moment 1 — Entry signal modal | feedback_loop | Modal after Draft Canvas asks whether the conversation revealed new territory; routes to feedback sheet. | Alpha | P0 | not_started | 0 |  | Matthew | F-003,F-017 |  | 12 | 0 | AUDIT 2026-05-16: Nothing exists. BrandCanvas page has no first-view detection, no modal, no 'entry signal' question copy, no moment-tagged write path. Greenfield build needed. | 2026-05-25
F-014 | Feedback Moment 2 — Use intent inline panel | feedback_loop | Inline panel after Forensic Canvas asks what the user intends to do with it (and surfaces asset-update demand signal). | Alpha | P0 | not_started | 0 |  | Matthew | F-008,F-017 |  | 12 | 0 | AUDIT 2026-05-16: Nothing exists. No inline panel, no 'use intent' multi-select, no 'update existing assets' option (which drives the asset-tracking gate), no moment-2 write path. Greenfield build needed. | 2026-05-25
F-015 | Feedback Moment 3 — 14-day async email | feedback_loop | Day-14 email asks what the user has actually done with the canvas and what's missing. | Alpha | P0 | not_started | 0 |  | Matthew | F-017 |  | 8 | 0 | AUDIT 2026-05-16: Nothing exists. No scheduled-send infrastructure (pg_cron not enabled, no day-offset queue), no 14-day email template, no inbound reply parsing. Resend exists only for synchronous send-framework-email (different feature). Greenfield build needed. | 2026-05-25
F-016 | Feedback response sheet integration | infrastructure | All three feedback moments write to a single sheet (Google Sheets or Supabase view) Matthew can monitor daily. | Alpha | P0 | not_started | 0 |  | Matthew |  |  | 8 | 0 | AUDIT 2026-05-16: Existing beta_feedback table is wide-form (overall_rating/liked_most/improvements/issues) — wrong shape for moment-tagged events. Need new feedback_events table with (moment, user_id, timestamp, payload JSONB). Existing BetaFeedback infrastructure will NOT compose — treat as separate older system; build moment infra fresh. | 2026-05-25
F-017 | Error monitoring | infrastructure | Sentry (or equivalent) capturing client + edge function errors. Daily review during alpha. | Alpha | P0 | not_started | 0 |  | Matthew |  |  | 6 | 0 | AUDIT 2026-05-16: Nothing exists. No Sentry/Rollbar/Bugsnag/LogRocket/Datadog in package.json. ErrorBoundary.tsx only console.errors with a commented placeholder. No source-map upload, no CI workflows directory. Greenfield install. | 2026-05-25
F-018 | Tester onboarding flow | accounts | One-page Loom + in-app welcome that frames alpha state and the three feedback moments. | Alpha | P0 | in_progress | 13 |  | Matthew |  |  | 8 | 0 | AUDIT 2026-05-16: BetaWelcome page exists at /beta but is a self-serve registration form gated by localStorage — not auto-shown on first login, doesn't name Trevor or framework, not dismissable. StartHere has a Vimeo intro (not Loom). No invitation template, no 'first 10'/'7-day'/'30-min debrief' language. Resend not configured for invitations. | 2026-05-25
F-019 | Pay gate (freemium) | pay_gate | Freemium model. Free = core tools + The Signature + limited AI; paid (£29/mo; one-off £67 notional/TBD) unlocks AI-heavy features (Review Lab analysis, unlimited prompts/iterations). Stripe + post-payment action menu. | Beta | P0 | not_started | 0 |  | Matthew | F-008 | P-012 | 40 | 0 | Central conversion test of beta. Pay-gate previews must use real canvas data. GEN3 (2026-05-25): reframed from two pricing tiers to freemium; canvas fields locked-but-visible for non-subscribers (F-064) [F 144128256 @32:26-34:29]. | 2026-05-25
F-020 | Create mode — Amazon listing copy | create_mode | Generate Amazon listing copy from Forensic Canvas using Trevor-voice prompts. | Beta | P0 | not_started | 0 |  | Matthew | F-008,F-019 | P-004,P-005 | 32 | 0 | First Create-mode output. Anchors the pay-gate preview. | 2026-05-25
F-021 | Create mode — Brand Voice Guide | create_mode | Generate Brand Voice Guide document from Forensic Canvas. | Beta | P0 | not_started | 0 |  | Matthew | F-008,F-019 | P-004,P-005 | 24 | 0 |  | 2026-05-25
F-022 | Coach mode v1 | coach_mode | Open conversation with full canvas context and document upload support. | Beta | P0 | not_started | 0 |  | Matthew | F-008 | P-001,P-007,P-010 | 56 | 0 | Required to deliver the £29/mo subscription value prop per Trevor's spec. GEN3 (2026-05-25): Coach auto-briefed on Diagnostic + Avatar data — no manual re-paste (fixes Gen-1 CX) [F 144128256 @34:29]. | 2026-05-25
F-023 | Export — PDF and Word | export | PDF and Word exports of both Draft and Forensic canvases. | Beta | P0 | in_progress | 65 |  | Matthew | F-003,F-008 | P-003 | 24 | 0 | PDF + Markdown shipped: BrandCanvasPDFExport, MarkdownPDFExporter, BrandMarkdownExport, generate-brand-strategy-pdf edge function. Word (.docx) export is the remaining gap. Once Draft/Forensic tier split lands in F-003/F-008, ensure both tiers export. | 2026-05-25
F-024 | Analytics + funnel tracking | analytics | PostHog or Mixpanel events on every funnel step; cohort analysis enabled. | Beta | P0 | not_started | 0 |  | Matthew |  |  | 16 | 0 | Conversion data is the whole point of beta. | 2026-05-25
F-025 | Support workflow | infrastructure | Intercom (or email) inbox with documented SLA; paying users get answers. | Beta | P0 | not_started | 0 |  | Matthew |  |  | 8 | 0 | Refund-rate risk is partly a support-responsiveness problem. | 2026-05-25
F-026 | ROI testimonial harvest email sequence | feedback_loop | Day-0, day-14, day-30, day-60 emails plus debrief invite when results report positive. | Beta | P0 | not_started | 0 |  | Matthew | F-015 |  | 12 | 0 | Target: 5+ verified testimonials by end of Beta; 10+ within 3 months. | 2026-05-25
F-027 | Brand Diagnostic integration | conversation | Diagnostic CTA dynamic (Brand Coach vs strategist) + score handoff into Layer 1 + visual identity refresh. | Beta | P0 | in_progress | 70 |  | Matthew |  | P-011 | 20 | 0 | Diagnostic largely exists (FreeDiagnostic + BetaFeedback components). Handoff into Layer 1 still loose. GEN3 (2026-05-25): feeds the Trust Gap™ Score (F-057); beta signup capture writes to the same DB [F 140678453 @16:26]. | 2026-05-25
F-028 | Asset Inventory v1 | asset_tracking | User can add assets, tag type (listing/email/social/ad/landing/product/other), mark alignment status manually. | Beta | P1 | not_started | 0 | Conditional on Alpha decision gate | Matthew | F-014 | P-009 | 40 | 0 | DEFERRED DECISION. Gate at end of Alpha. Default is NO. Trevor's Gen 3 spec does not include asset tracking — only ship if Moment 2 signal is ≥40%. | 2026-05-25
F-029 | Asset Inventory v1.5 — Canvas linkage | asset_tracking | Mark asset as aligned to a specific canvas version; later canvas updates flag asset as stale. | Beta | P1 | not_started | 0 | Conditional on F-028 | Matthew | F-028 | P-009 | 32 | 0 | Introduces the temporal signal — user can see what's out of date. | 2026-05-25
F-030 | Asset Inventory v2 — Diff surface | asset_tracking | When canvas changes, show user a list of likely-affected assets with diff reason (Trigger Moment changed, voice changed, etc.). | GA | P1 | not_started | 0 | Conditional on F-029 | Matthew | F-029 | P-009 | 56 | 0 | Likely a GA-era feature per brief; listed for completeness. | 2026-05-25
F-031 | My Brands dashboard | accounts | Multi-brand dashboard with brand switcher; users can manage 2+ brands. | GA | P0 | not_started | 0 |  | Matthew | F-046 | P-007 | 40 | 0 | Power users will have multiple brands; product caps out at one customer without this. | 2026-05-25
F-032 | Anonymous-to-authenticated migration | accounts | Diagnostic completers without accounts have their data preserved on signup. | GA | P0 | not_started | 0 |  | Matthew | F-027 |  | 16 | 0 | Top-of-funnel users drop off without this. | 2026-05-25
F-033 | Self-serve onboarding tour | design_system | Tooltip-light onboarding tour; no human needed to start. | GA | P0 | not_started | 0 |  | Matthew |  |  | 16 | 0 | Public launch means support cost scales with users — self-serve protects margin. | 2026-05-25
F-034 | Pricing page (cold-traffic optimised) | pay_gate | Standalone pricing page that converts cold traffic; A/B tested in late beta. | GA | P0 | not_started | 0 |  | Matthew | F-019 |  | 16 | 0 | Conversion surface for non-warm visitors. | 2026-05-25
F-035 | Status page | infrastructure | Public uptime page + incident communication channel. | GA | P0 | not_started | 0 |  | Matthew |  |  | 8 | 0 | Trust signal required for paid users. | 2026-05-25
F-036 | Knowledge base | infrastructure | 10–20 articles seeded from Beta support tickets covering common questions. | GA | P0 | not_started | 0 |  | Matthew | F-025 |  | 24 | 0 | Reduces ticket volume and improves time-to-value. | 2026-05-25
F-037 | Refund policy + ToS + Privacy Policy | infrastructure | Standard SaaS refund (14-day), Terms of Service, Privacy Policy. | GA | P0 | not_started | 0 |  | Matthew |  |  | 8 | 0 | Legal hygiene required for paid public product. | 2026-05-25
F-038 | Performance metrics tracking | analytics | Per-avatar manual entry of ROAS, CTR, CPA, conversion rate, custom metrics. Drives ROI testimonials. | GA | P0 | not_started | 0 |  | Matthew | F-046 | P-010 | 32 | 0 | OPEN QUESTION: existing V2 PRD scopes this as a P0 V2 feature. Trevor's Gen 3 spec does not address it. Treated here as GA P0; needs Matthew sign-off. | 2026-05-25
F-039 | Referral programme | infrastructure | In-product referral mechanism with 20% rev share. | GA | P1 | not_started | 0 |  | Matthew | F-019 |  | 24 | 0 | Acquisition lever from GA Plan. | 2026-05-25
F-040 | Affiliate tracking infrastructure | infrastructure | Partner affiliate links, attribution, payout reporting. | GA | P1 | not_started | 0 |  | Matthew |  |  | 24 | 0 | Brand strategist partner channel needs attribution before outreach. | 2026-05-25
F-041 | SEO foundation | infrastructure | Sitemap, schema markup, content templates for long-tail brand strategy queries. | GA | P1 | not_started | 0 |  | Matthew |  |  | 20 | 0 | Three-month organic ramp — start at beginning of beta to earn GA traffic. | 2026-05-25
F-042 | Avatar comparison view | avatar_builder | Side-by-side comparison of two avatars (different segments, different brands). | GA | P1 | not_started | 0 |  | Matthew | F-031 | P-008 | 24 | 0 | Power-user feature; rewards multi-canvas usage. | 2026-05-25
F-043 | Field edit history viewer | avatar_builder | Audit log per field showing edit history and which canvas version each value was active in. | GA | P1 | not_started | 0 |  | Matthew | F-046 | P-009 | 16 | 0 | Schema needs field_edit_history table. | 2026-05-25
F-044 | Bulk operations | avatar_builder | Copy fields between avatars; find/replace across an avatar. | GA | P1 | not_started | 0 |  | Matthew | F-031 |  | 20 | 0 | Power-user feature. | 2026-05-25
F-045a | TikTok-specific landing page | design_system | Variant landing page optimised for TikTok cold traffic. | Post-GA | P1 | not_started | 0 |  | Matthew | F-034 |  | 12 | 0 | TikTok integration is GA+4wks per Launch Roadmap; not a build dependency. | 2026-05-25
F-045b | UTM tagging across TikTok touchpoints | analytics | Consistent UTM scheme on every TikTok-originating link. | Post-GA | P1 | not_started | 0 |  | Matthew | F-024 |  | 4 | 0 |  | 2026-05-25
F-045c | TikTok Pixel integration | analytics | TikTok Pixel installed on landing pages and conversion events. | Post-GA | P1 | not_started | 0 |  | Matthew |  |  | 4 | 0 |  | 2026-05-25
F-045d | Self-report attribution question on signup | analytics | 'Where did you hear about us?' on signup; option for TikTok and named creators. | Post-GA | P1 | not_started | 0 |  | Matthew |  |  | 4 | 0 | Pairs with UTM data to triangulate true attribution. | 2026-05-25
F-046 | Database migrations (additive) | infrastructure | Migrations for brands, avatars, avatar_profiles, brand_strategies, performance_metrics, field_edit_history, assets (if asset tracking ships). | Alpha | P0 | in_progress | 50 |  | Matthew |  |  | 24 | 0 | Additive only. RLS policies in F-047. | 2026-05-25
F-047 | RLS policies for new tables | infrastructure | Row-level-security policies on every new table created in F-046. | Alpha | P0 | in_progress | 40 |  | Matthew | F-046 |  | 12 | 0 |  | 2026-05-25
F-048 | Edge functions | infrastructure | conversation, canvas-synthesis, create-copy, coach-conversation, voice-of-customer-analysis edge functions. | Alpha | P0 | in_progress | 40 |  | Matthew |  |  | 40 | 0 | idea-framework-consultant exists; Gen 3 functions partially overlap. Audit needed. | 2026-05-25
F-049 | RAG integration with System KB | infrastructure | Retrieval from the existing System KB vector store (vs_6948707b318c81918a90e9b44970a99e) in all relevant edge functions. | Alpha | P0 | in_progress | 60 |  | Matthew | F-048 | P-007 | 16 | 0 | OpenAI embeddings removed in commit 260128b (consolidated to Claude/internal embeddings) — verify RAG pipeline still wired. | 2026-05-25
F-050 | Feature flag system | infrastructure | Ensure useFeatureFlag gates every V2/Gen 3 route; flags toggle independently. | Alpha | P0 | in_progress | 80 |  | Matthew |  |  | 8 | 0 | Hook already exists. Audit V2 routes for missing gates. | 2026-05-25
F-051 | Pre-implementation refactoring sprint | infrastructure | Week-0 refactoring sprint per V2 PRD: service extraction, field sync architecture, component composition. | Alpha | P0 | in_progress | 70 |  | Matthew |  |  | 40 | 0 | Refactor patterns shipped (SupabaseChatService split, FieldSyncService, AIAssistant decomposition). Verify all Gen 3 work picks up new patterns. | 2026-05-25
F-053 | Multiple positioning angles per avatar | avatar_builder | Support multiple positioning / marketing angle variants for the same avatar — each angle has its own brand strategy doc / canvas section, but shares the underlying avatar. | Beta | P1 | not_started | 0 |  | Matthew | F-008,F-031 | P-003,P-008,P-010 | 40 | 0 | Validates A/B angle testing for paying users. Each angle = a strategy variant tied to a canonical avatar. Surfaces in Coach mode and Export. OPEN: schema choice — separate canvases per angle vs angle-tagged sections within one canvas. | 2026-05-25
F-054 | Image asset side-by-side comparison and tracking | asset_tracking | Upload current image/video assets, view side-by-side, tag against avatar + angle, flag gaps and emotional-connection opportunities. | GA | P1 | not_started | 0 | Conditional on F-028 (asset tracking decision) | Matthew | F-028,F-053 | P-006,P-009 | 56 | 0 | Extension of asset_tracking that goes beyond text. Anchored to InfinityVault need N-002 (assess images/videos, identify what's missing, surface emotional-connection opportunities). Requires image storage (Supabase Storage) and a comparison UI. | 2026-05-25
F-055 | Design brief creation | create_mode | Generate a design brief document from the Forensic Canvas + selected positioning angle. Output briefs creative work (image, video, packaging) for designers or agencies. | Beta | P1 | not_started | 0 |  | Matthew | F-008,F-053 | P-004,P-006,P-008 | 32 | 0 | Sibling to F-020 (Amazon listing copy) and F-021 (Brand Voice Guide). Bridges the canvas to creative work. Required to make F-054 actionable (gap → brief → asset). | 2026-05-25
F-056 | Image generation — deliberate non-goal | create_mode | NOT building. Deliberate non-goal: position IDEA as the brand brief upstream of image tools like Pixii — 'build your brand brief in IDEA, execute anywhere.' | Post-GA | P2 | not_started | 0 |  | Matthew | F-055 |  | 80 | 0 | DECISION (2026-05-25): deliberate non-goal, not a backlog item. Image gen needs separate infra + ongoing cost and doesn't improve the core understanding product. Strategy: be the brief upstream of Pixii [Analysis 2026-05-17 'On Image Generation']. Pending Matthew formal sign-off to fully cut. | 2026-05-25
F-052 | Lovable.dev vs existing codebase decision | infrastructure | Architectural decision: build Gen 3 in Lovable.dev (per Trevor) or extend existing React codebase. Critical risk per Launch Roadmap. | Alpha | P0 | complete | 100 |  | Matthew |  |  | 4 | 0 | RESOLVED 2026-04-23 [F 140678453]: split dev — Matthew builds backend in Claude Code, Trevor builds the marketing site in Lovable; beta stays on Lovable; ideabrandcoach.com on the same codebase/DB initially; custom server deferred until traction. R-013 downgraded to resolved. | 2026-05-25
F-057 | Trust Gap™ Score results screen | conversation | Diagnostic results reframed as an aggregated Trust Gap™ Score (e.g. 73) that flags the widest-gap pillar (e.g. empathy). Same 6 questions / 4 pillars; UI + copy only, logic unchanged. | Alpha | P0 | not_started | 0 |  | Matthew | F-027 | P-011 | 12 | 0 | GEN3 (2026-05-25): the Alpha hook — the #1 thing to validate (must resonate). Underlying diagnostic logic already exists ('all of that code exists as is'); this is the score-screen reframe [F 144128256 @01:45,@05:00]. | 2026-05-25
F-058 | The Decision Trigger™ capture (Stage 2B) | avatar_builder | Dedicated screen capturing the event that made the customer act today (the photograph, the comment, the wedding). Was previously only a canvas field. | Alpha | P0 | not_started | 0 |  | Matthew | F-059 | P-001 | 16 | 0 | GEN3 (2026-05-25): blue-water line #2 vs Pixii — operates at the level of WHEN the customer is ready to act, not just who they are [F 144128256 @09:13-14:50]. | 2026-05-25
F-059 | Bridge screen (diagnostic → avatar) | conversation | Two screens that quote the user's empathy score and explain why building the avatar is the next step. 'A good coach wouldn't just present a score and move on.' | Alpha | P0 | not_started | 0 |  | Matthew | F-057 | P-011 | 10 | 0 | GEN3 (2026-05-25): connective tissue that turns the Trust Gap score into momentum into the avatar build [F 144128256 @07:20]. | 2026-05-25
F-060 | The Signature (Stage-5 output) | avatar_builder | One-sentence customer truth — e.g. 'My customer isn't buying shampoo; they're buying the feeling of still being in control of how they age.' The output of the research stages. | Alpha | P0 | not_started | 0 |  | Matthew | F-004,F-005,F-006,F-007 | P-001,P-002 | 20 | 0 | GEN3 (2026-05-25): THE retention / word-of-mouth moment. MVP must validate this + the Trust Gap™ Score first; everything else is downstream [Analysis 2026-05-17]. A draft Signature may surface earlier at the Draft Canvas (F-003). | 2026-05-25
F-061 | "Before State" emotional prompt screen | avatar_builder | Prompts the user to articulate the customer's emotional 'before' state as part of the avatar build. | Alpha | P1 | not_started | 0 |  | Matthew |  | P-002 | 8 | 0 | GEN3 (2026-05-25): MVP ships static example text; AI-suggestion path deferred (see F-009) [F 144128256 @09:13]. | 2026-05-25
F-062 | Decision Mode sliders | avatar_builder | Slider inputs for shopper type (Shopify 4 types), researcher-vs-gut, stakes, and loyalty — so users needn't type free text. | Alpha | P1 | not_started | 0 |  | Matthew |  | P-002 | 14 | 0 | GEN3 (2026-05-25): lowers friction in the avatar build [F 144128256 @22:00-25:16]. | 2026-05-25
F-063 | Review Lab (competitor + own review analysis) | create_mode | 'Research mode' that analyses competitor and own reviews. MVP = CSV / pasted-text upload (no scraping) to de-risk; AI analysis is a paid-tier feature. | Beta | P1 | not_started | 0 |  | Matthew | F-019 | P-005 | 32 | 0 | GEN3 (2026-05-25): paid-tier AI work behind the freemium gate (F-019). MVP deliberately avoids scraping [F 144128256 @16:31-18:47]. | 2026-05-25
F-064 | Locked-but-visible canvas fields (free tier) | pay_gate | Non-subscribers see canvas fields locked rather than hidden, to entice signup/upgrade. | Beta | P0 | not_started | 0 |  | Matthew | F-019 | P-012 | 16 | 0 | GEN3 (2026-05-25): core freemium conversion mechanic [F 144128256 @28:50-32:01]. | 2026-05-25
F-065 | "Skip avatar" / self-populate path | canvas | Lets a user skip the avatar build and self-populate the canvas, with an 'avatar not complete' reminder. | Beta | P2 | not_started | 0 |  | Matthew |  |  | 10 | 0 | GEN3 (2026-05-25): Matthew ambivalent — keep loosely scoped [F 144128256 @29:22]. | 2026-05-25
F-066 | Landing-page A/B split test (ProductPinion) | analytics | Split-test V1 (ChatGPT-built, polished) vs V2 (Claude-built, simpler) landing pages. | Alpha | P1 | not_started | 0 |  | Matthew | F-067 |  | 12 | 0 | GEN3 (2026-05-25): confirm ProductPinion supports landing-page split testing (R-019); else build scaffolding [F 140678453 @29:25-34:09]. | 2026-05-25
F-067 | Marketing site on ideabrandcoach.com (same codebase/DB) | infrastructure | Public marketing site; app gated, revealing feature sets as they become beta-ready. Same codebase/DB initially. | Alpha | P0 | not_started | 0 |  | Matthew |  |  | 24 | 0 | GEN3 (2026-05-25): old consultancy site expires June. Trevor owns this track in Lovable (split-dev, F-052) [F 140691318 @00:19,@00:42]. | 2026-05-25

## Sub-features
Sub-features — shippable units per feature
subfeature_id | parent_feature_id | subfeature_name | description | acceptance_criteria | status | percent_complete | effort_estimate_hours | actual_hours | blocker | notes
F-001.1 | F-001 | 10-question script in Trevor's voice | Source the 10 Layer 1 questions and Trevor-voice phrasing from IDEA_KNOWLEDGE.md. | All 10 questions stored in prompt config and rendered in order; Trevor reviews sample transcript. | not_started | 5 | 8 | 0 |  | Trevor persona prompt exists (idea-framework-consultant-claude/prompt.ts) and FIELD_QUESTIONS bank has 110 candidates (src/config/fieldQuestions.ts), but no 10-question script, no fixed rendering order, getFieldQuestion() is dead code.
F-001.2 | F-001 | Fallback responses for empty / off-topic input | When the user's reply doesn't extract a field, surface a Trevor-voice nudge instead of restating the question. | Off-topic input triggers fallback string; fallbacks vary by question; no robotic 'Please answer the question.' | not_started | 10 | 6 | 0 |  | Two empty-response fallbacks exist (edge function stream.ts:129-137 + ChatService:166-173) but they trigger on 'no text', not off-topic. No per-question fallback variation, no Trevor-voice phrasing.
F-001.3 | F-001 | Conversation state persistence | Layer 1 progress persists across reload via existing FieldSyncService. | Refreshing mid-conversation resumes at the last unanswered question with prior answers visible. | in_progress | 70 | 6 | 0 |  | Session + message + chapter-progress persistence all work and survive refresh (useChatSessions, useChat, useChapterProgress); missing piece is an explicit 'last unanswered question' pointer (free-form conversation has no scripted position to resume to).
F-001.4 | F-001 | Streaming response rendering | Assistant replies stream token-by-token via SSE. | User sees streaming text within 500ms of submit; SSE error states render a Trevor-voice fallback. | in_progress | 65 | 8 | 0 |  | Streaming pipeline (edge SSE → ChatStreamParser → React state → ChatMessageList) is wired end-to-end and works; SSE-error-to-Trevor-voice fallback NOT met (errors render as generic destructive toast). No <500ms latency assertion.
F-001.5 | F-001 | Mobile keyboard / viewport handling | Conversation UI works on mobile without keyboard-induced layout breaks. | iOS Safari and Android Chrome both render correctly with keyboard open; input stays visible. | in_progress | 25 | 6 | 0 |  | Basic mobile-friendly touch targets, pb-safe padding, and 16px font (avoids iOS zoom) in ChatInputBar; missing VisualViewport API usage, keyboard-show scroll-into-view, and no cross-device validation.
F-002.1 | F-002 | Subscribe sidebar to field extraction events | Sidebar listens for new/updated field extractions and rerenders affected cards. | Extracting a field during conversation updates the corresponding sidebar card within 1s. | in_progress | 80 | 8 | 0 |  | Field-extraction events flow edge SSE → useChat → useFieldExtractionOrchestrator → ChapterSectionAccordion (auto-expands affected chapter, surfaces pending ghost values); behaviour-complete but no latency test and applied via 'pending ghost' rather than direct write.
F-002.2 | F-002 | Confidence-score badges on sidebar fields | Each populated sidebar field shows the quality / confidence badge (already shipped for V2 — port to Layer 1). | Low-confidence fields show amber badge; high-confidence shows green; matches existing badge design. | in_progress | 75 | 4 | 4 |  | Quality badges render with tiered colors on sidebar fields (ChapterFieldSet:112-135), but they reflect value-quality heuristics (fieldQualityScore.ts word-count/specificity) rather than the AI extraction confidence score — acceptance criterion 'low-confidence amber, high-confidence green from extractor confidence' is not literally met.
F-002.3 | F-002 | Sidebar collapse / expand on mobile | Mobile users can collapse sidebar to focus on conversation. | Hamburger toggle hides sidebar; state persists across navigation. | in_progress | 40 | 4 | 0 |  | Mobile sheet overlay for chapter panel works (TwoPanelTemplate:129-141 + BookOpen-icon toggle); state is in-memory only (useState in useBrandCoachV2State), does not persist across navigation; trigger is BookOpen icon, not hamburger.
F-003.1 | F-003 | DRAFT badge component | Visual badge on Draft Canvas distinguishing it from Forensic Canvas. | Badge visible above-fold on canvas page; uses gold / amber tone from design tokens. | not_started | 0 | 4 | 0 |  | No DRAFT badge component. Tier distinction is conceptual only — grep across src/ + edge functions for 'DRAFT'/'tier'/'forensic' returns ~zero structural hits. Gold/amber tokens exist (hsl(var(--gold-warm))) as mount-ready primitives.
F-003.2 | F-003 | Synthesis edge function with Trevor prompt | canvas-synthesis edge function takes Layer 1 transcript + extracted fields, returns Draft Canvas JSON. | Returns all Draft-tier fields populated; fields with low confidence flagged; latency <8s. | in_progress | 55 | 12 | 0 |  | Per-section synthesis with Trevor voice (generate-brand-strategy-section + voice.ts TREVOR_VOICE_DIRECTIVE on Haiku) exists but generates the full document — no Draft-tier subset, no low-confidence flagging, no <8s latency guarantee. Reusable as Draft once a tier filter is added.
F-003.3 | F-003 | Forensic upgrade CTA | Draft Canvas surfaces a prominent CTA inviting user into the Avatar Builder. | CTA visible in canvas top-bar AND inline after the most synthesis-light section. | not_started | 0 | 4 | 0 |  | No Forensic upgrade CTA anywhere. BrandCoachHeader and inline section locations exist as natural mount points; 'upgrade' string returns no matches in BrandCanvas.tsx/BrandCoachV2.tsx.
F-003.4 | F-003 | Coherence pass | Synthesis avoids contradictions between fields (e.g., aspirational language in one field vs jaded in another). | Manual review of 5 sample draft canvases shows no contradictions; Trevor signs off. | not_started | 0 | 4 | 0 |  | Blocked on F-003.1/F-003.2 producing a distinct Draft output to review. Trevor sign-off process not documented in repo.
F-004.1 | F-004 | Field schema for Psychographic Profile | Define the field set from Gen 3 spec (values, identity, worldview, lifestyle). | Schema documented and reviewed against Gen 3 brief; types defined in TypeScript. | in_progress | 60 | 4 | 0 |  | TypeScript schema (AvatarPsychographics in src/types/avatar.ts) matches Gen 3 (values/fears/desires/triggers arrays) and persists via avatars table JSONB column. BUT: V2 chapter UI (CUSTOMER_AVATAR chapter in chapterFields.ts:176-220) flattens into two coarse textareas; Avatar 2.0 five-field discrete schema (skills/04-avatar-five-fields.md) NOT modelled as typed fields.
F-004.2 | F-004 | Section UI with progressive disclosure | Section renders one cluster at a time, expanding as the user advances. | User sees no more than ~4 fields at once on mobile. | in_progress | 70 | 12 | 0 |  | Accordion delivers '<=4 fields at once on mobile' (ChapterSectionAccordion:241-289 + active-chapter-only-open pattern; mobile Sheet via TwoPanelTemplate). Progressive disclosure is at chapter level, not Gen 3 sub-section level.
F-004.3 | F-004 | AI assistance modes wired | Each field supports the four AI assistance modes from F-009. | All four mode buttons present per field; each routes to the right edge function. | in_progress | 35 | 8 | 0 |  | Three of four AI modes exist as shared infra (ghost text via GhostTextFieldWrapper; review modal via AdaptiveFieldReview; chat-extracted badges via FieldExtractionBadges). The fourth (FieldChatButton used in V1 AvatarBuilder) is NOT integrated into V2 ChapterFieldSet.
F-004.4 | F-004 | Persistence and resume | Section state persists via FieldSyncService and resumes on reload. | Closing browser mid-section and reopening restores all entered values. | complete | 90 | 4 | 0 |  | Persistence + resume via FieldPersistenceService + localStorage + realtime subscription (useFieldExtraction:104-449). Tested in src/hooks/__tests__/useFieldExtraction.test.tsx.
F-004.5 | F-004 | Completion gate to next section | User can advance to Section 2 once Section 1 is in a valid state (not necessarily 100% — Trevor wants flow, not gates). | Advance button enables when required-minimum fields are filled; soft prompt for empty optional fields. | in_progress | 55 | 4 | 0 |  | Validation logic in useChapterProceeding (58-131): all-required-fields check, auto-accept pending ghost text, flash first empty field. BUT: button surface not mounted in BrandCoachV2.tsx render tree. 'Required-minimum' enforcement is all-required, not Gen 3 minimum-subset.
F-005.1 | F-005 | Field schema for Buying Behaviour | Define fields: purchase triggers, objections, decision criteria, channels, price sensitivity. | Schema documented; matches Gen 3 brief. | in_progress | 55 | 4 | 0 |  | AvatarBuyingBehavior type (src/types/avatar.ts:48-60) with persistence exists. BUT: V2 chapter map has no dedicated 'Buying Behaviour' chapter — closest is BUYER_INTENT which is conceptually buyer-intent not buying-behavior. Shopper Type taxonomy (skills/04) not codified.
F-005.2 | F-005 | Section UI | Progressive disclosure UI for the section, consistent with F-004. | Visual parity with Section 1; mobile-first layout. | in_progress | 40 | 12 | 0 |  | V1 AvatarBuilder.tsx:309 has a 'Buying Behavior' tab with the right fields. V2 (the surface being tracked) does NOT have a discrete Buying Behaviour chapter; data shape exists but UI is split between V1 tab and V2 BUYER_INTENT chapter.
F-005.3 | F-005 | AI assistance wired | All four AI assistance modes available per field. | All buttons present and functional. | in_progress | 35 | 8 | 0 |  | Same gap as F-004.3 — three of four AI modes via shared ChapterFieldSet; FieldChatButton (V1 only) missing from V2.
F-005.4 | F-005 | Persistence and resume | Section state persists and resumes via FieldSyncService. | Closing and reopening restores state. | complete | 90 | 4 | 0 |  | Persistence via shared FieldPersistenceService + realtime subscription; closing/reopening restores via DB + localStorage merge.
F-006.1 | F-006 | Field schema for Emotional Journey Mapping | Define fields: pre-purchase emotions, during-purchase emotions, post-purchase emotions, Trigger Moment. | Schema documented; Trigger Moment flagged as the most important. | in_progress | 30 | 4 | 0 |  | Emotional fields exist (EMOTIONAL_CONNECTION chapter:378-413 + CUSTOMER_EXPERIENCE chapter:415-450) but Gen 3 'Emotional Journey Mapping' framing with distinguished Trigger Moment NOT present; emotionalTriggers is a flat array, not a journey.
F-006.2 | F-006 | Trigger Moment field surfacing | Trigger Moment field uses elevated visual treatment (gold accent, larger label). | Field visually dominant in section; matches design tokens. | not_started | 0 | 4 | 0 |  | 'Trigger Moment' as a distinct field with elevated visual treatment does not exist. Zero matches for 'Trigger Moment'/'trigger_moment' in src/. ChapterFieldSet renders all fields identically; no per-field visual emphasis system.
F-006.3 | F-006 | Section UI | Progressive disclosure UI consistent with F-004. | Visual parity with prior sections. | in_progress | 70 | 12 | 0 |  | Same accordion progressive-disclosure mechanics as F-004.2 apply to EMOTIONAL_CONNECTION chapter (3 fields, under 4-field mobile target).
F-006.4 | F-006 | AI assistance wired | All four AI assistance modes available per field, including specific Trigger-Moment-shaped prompts. | AI buttons functional; Trigger Moment prompts pull example trigger language. | in_progress | 25 | 12 | 0 |  | General AI assistance carries through; no Trigger-Moment-specific prompts in brand-ai-assistant/index.ts or idea-framework-consultant-claude/.
F-006.5 | F-006 | Persistence and resume | Section state persists and resumes. | Closing and reopening restores state. | complete | 90 | 4 | 0 |  | Inherited from shared FieldPersistenceService + realtime subscription.
F-007.1 | F-007 | Review paste-in UI | User can paste in 5-50 customer reviews / testimonials; UI handles long-form text well. | Textarea accepts pasted content; preview shows reviews chunked and counted. | in_progress | 50 | 8 | 0 |  | Review intake exists but is URL/ASIN-driven via ReviewAnalyzerModal:199-219 (scrape model), not the Gen 3 paste-raw-reviews-and-chunk model. V1 has a raw voiceOfCustomer textarea (AvatarBuilder.tsx:140-146).
F-007.2 | F-007 | voice-of-customer-analysis edge function | Edge function extracts verbatim copy hooks, common phrases, and emotional language from pasted reviews. | Returns ranked list of phrases with frequency + emotional valence; latency <15s for 25 reviews. | in_progress | 25 | 16 | 0 |  | voice-of-customer-analysis edge function does NOT exist. review-scraper / review-scraper-deep edge functions exist but only scrape, don't rank phrases with frequency + valence. V1 analysis (analyzeVoiceOfCustomer at AvatarBuilder.tsx:217-274) is fully MOCKED (setTimeout + hardcoded data).
F-007.3 | F-007 | Extracted phrases UI | Show extracted phrases as cards user can flag as 'use this' or 'discard'. | Flagging persists; flagged phrases populate Forensic Canvas Voice fields. | not_started | 10 | 8 | 0 |  | No extracted-phrase UI with use/discard actions exists. V1 shows mock keyPhrases as text; ReviewAnalyzerModal shows review counts + ratings, no phrase-level flag-and-keep cards.
F-007.4 | F-007 | Persistence and resume | Pasted reviews and flagged phrases persist across sessions. | Closing and reopening restores state. | in_progress | 35 | 4 | 0 |  | Raw voiceOfCustomer paste persists via usePersistedField in V1; flagged phrases have no persistence because the flag UI doesn't exist.
F-008.1 | F-008 | 28+ field canvas schema | Define every Forensic Canvas field per Gen 3 brief. | Schema documented; field list matches brief. | in_progress | 70 | 4 | 0 |  | 35-field canvas schema exists across 11 chapters (src/config/chapterFields.ts:99-537 + src/types/chapter.ts; UI confirms '35 fields captured'). Exceeds 28+ threshold but no explicit 'Forensic Canvas' label; field-by-field Gen 3 reconciliation outstanding.
F-008.2 | F-008 | Synthesis edge function (Forensic tier) | canvas-synthesis edge function in Forensic mode pulls from all 4 Avatar Builder sections. | Returns populated Forensic Canvas JSON; differentiated from Draft synthesis. | in_progress | 50 | 16 | 0 |  | Full-canvas synthesis works end-to-end (two paths: generate-brand-strategy-document v1/gpt-4o 1164L; generate-brand-strategy-section v2/Haiku per-section + MarkdownExportService orchestration). No Draft/Forensic differentiation — single unified pipeline; output is Markdown not enforced JSON. v1/v2 are pipeline versions, NOT tier versions.
F-008.3 | F-008 | Trigger Moment 'Strategic Entry Point' callout | Forensic Canvas displays Trigger Moment in a prominent callout block labelled Strategic Entry Point. | Callout visible above-fold on canvas page. | not_started | 0 | 4 | 0 |  | 'Trigger Moment' / 'Strategic Entry Point' concept absent from code — zero structural hits across src/ and edge functions. No field, callout, schema entry, or generator section captures it.
F-008.4 | F-008 | Draft-to-Forensic differential view | User can toggle between Draft and Forensic side-by-side to see the upgrade differential. | Toggle visible from canvas; renders both canvases readably on desktop and mobile. | not_started | 0 | 12 | 0 |  | No two synthesis outputs exist to compare (single unified path). No toggle component, no diff renderer. Prerequisites in F-003.2 + F-008.2 missing.
F-008.5 | F-008 | Export prep (Markdown intermediate) | Forensic Canvas serialises to Markdown as an intermediate format for F-023 PDF/Word export. | Markdown round-trips: re-importing reproduces canvas state. | in_progress | 75 | 4 | 0 |  | Markdown export pipeline is mature (MarkdownExportService + BrandMarkdownExport + templates/sections/ for BrandCanvas, CustomerAvatar, IDEAFramework, etc.). Round-trip (parse back into canvas) not implemented — export is one-way.
F-009.1 | F-009 | Mode: Think About This | Generates prompt-style question helping the user think more deeply about the field. | Returns 3-5 reflective questions in Trevor's voice; <5s latency. | not_started | 0 | 8 | 0 |  | No 'Think About This' mode. AIAssistant uses a single 'Generate with AI' button → brand-ai-assistant edge function whose prompt explicitly says 'Generate the ACTUAL content for the field, not suggestions or feedback' — opposite of reflective questions. contextual-help/index.ts exists but isn't wired to a 'Think About This' surface.
F-009.2 | F-009 | Mode: Real-World Examples | Returns 2-3 anonymised example fills for the field from RAG over the System KB. | Examples are relevant to the brand category; <8s latency. | not_started | 0 | 8 | 0 |  | No 'Real-World Examples' mode. brand-ai-assistant returns single suggestion text only. RAG infra (sync-diagnostic-to-embeddings) exists but for user KB, not anonymised System KB examples.
F-009.3 | F-009 | Mode: Get AI Suggestions | Returns 2-3 suggested fills based on the user's prior fields. | Suggestions are coherent with prior fields; <8s latency. | in_progress | 55 | 8 | 0 |  | Single-suggestion generator works end-to-end (AIAssistant → AISuggestionHandler → brand-ai-assistant edge function, with accept/reject preview). Missing the '2-3 alternatives' criterion and the explicit mode label.
F-009.4 | F-009 | Mode: Get AI Auto-Populate | Auto-fills the field with the best inferred value; user can accept / edit / reject. | Auto-fill respects manual edit lock (F-011); never overwrites manual edits silently. | in_progress | 35 | 12 | 0 |  | Chat-driven auto-extraction populates many fields with lock-skip logic (useFieldExtraction:179-248, line 192 skips locked); GhostTextFieldWrapper Tab-accept exists. NO dedicated per-field 'Auto-Populate' button. Manual-edit-aware overwrite is lock-based, not edit-flag-based.
F-009.5 | F-009 | Field-level mode selector UI | Each field shows the 4 mode buttons in a consistent place; tooltip explains each. | Buttons visible and accessible; consistent across all Avatar Builder sections. | not_started | 5 | 12 | 0 |  | No 4-mode selector UI. AIButton.tsx:32-52 is a single 'Generate with AI' button per field. Tooltip explaining modes absent.
F-010.1 | F-010 | Disclosure pattern documented in design system | Pattern guide written so all sections behave the same way. | Doc in design system; example component referenced. | not_started | 5 | 4 | 0 |  | shadcn Accordion is used informally as the chapter-disclosure pattern (ChapterSectionAccordion) but no documented disclosure pattern guide; docs/lovable/04_UI_DESIGN_SYSTEM.md doesn't formalise it.
F-010.2 | F-010 | Mobile-first audit on V2 sections | Audit existing V2 sections against mobile-primary use; document gaps. | Audit report committed; gaps tracked as sub-tasks of relevant features. | not_started | 0 | 4 | 0 |  | No mobile-first audit report committed. Responsive behaviour exists per-component (e.g., GhostTextFieldWrapper:102 hides on mobile) but no systematic audit document, no tracked gap list.
F-011.1 | F-011 | Manual-edit flag on field model | Persist a boolean per field indicating user has manually edited it. | Flag set on any non-AI edit; survives reload. | in_review | 70 | 4 | 4 |  | field_source: 'ai' ¦ 'manual' exists (useFieldExtraction:35-43, setFieldManual:299-312) and survives reload (FieldPersistenceService:65-125). NOT the same as a 'manuallyEdited' boolean — system pairs it with separate is_locked user-toggle. Spec ambiguity: manual edit alone does NOT trigger overwrite protection; only an explicit lock does.
F-011.2 | F-011 | AI overwrite guard | AI assistance modes never silently overwrite manually edited fields. | Auto-populate skips manual-edited fields by default; user can explicitly opt in to overwrite. | in_progress | 65 | 4 | 0 |  | AI overwrite guard works for chat extraction (useFieldExtraction:190-203) and realtime sync (399-422), but ONLY when user explicitly locked the field (useFieldLocking.setFieldLock). No automatic guard for manually-edited-but-unlocked fields. Per-field AIAssistant button bypasses lock entirely.
F-011.3 | F-011 | Visual indicator of manual edit | Manually edited fields show a small icon indicating they're locked. | Icon visible; tooltip explains the lock. | in_progress | 35 | 4 | 0 |  | Amber border/bg on FieldExtractionBadges:42-43 indicates lock, but no dedicated lock icon, no tooltip explaining it, no user-facing toggle. setFieldLock is only called programmatically.
F-012.1 | F-012 | Conversation→field extraction edge function | Edge function takes a conversation turn and returns structured field updates with confidence. | Returns field updates with confidence scores 0-1; latency <3s. | in_progress | 85 | 12 | 0 |  | Edge function returns field updates with 0-1 confidence via streaming tool-use (idea-framework-consultant-claude/tools.ts:54-93 + stream.ts:93-105); confidence flows through orchestrator; missing latency assertion/test and dedicated tool extraction tests.
F-012.2 | F-012 | Confidence score → quality badge mapping | Confidence scores map to the user-facing quality badge tiers. | Mapping documented; consistent across fields. | in_progress | 50 | 4 | 4 |  | Two distinct badge systems exist (heuristic quality tiers on sidebar via fieldQualityScore.ts; raw percentage on chat badges in FieldExtractionBadges:194-198) but neither is a documented confidence→badge mapping — spec criterion 'Mapping documented; consistent across fields' is not met.
F-012.3 | F-012 | Re-extraction on field edit | When user edits a field, re-extract from the user's own prose if it looks like a paragraph. | Pasting a paragraph into a single field offers extraction into multiple fields. | not_started | 0 | 8 | 0 |  | No re-extraction-on-edit behaviour. Pasting a paragraph into a single field just stores it as that field's value with no offer to split. ChapterFieldSet handleInputChange has no multi-field detection.
F-013.1 | F-013 | Modal trigger after Draft Canvas | Modal opens automatically the first time a user views their Draft Canvas. | Modal appears once per user; dismissable; trigger not repeated. | not_started | 0 | 4 | 0 |  | No modal trigger exists. BrandCanvas page has no first-view detection or modal mounting; nothing distinguishes 'Draft' vs 'Forensic' canvas state.
F-013.2 | F-013 | Feedback questions (per Launch Roadmap › Feedback Loop) | Three short questions about whether the conversation revealed new territory. | Questions match Launch Roadmap spec exactly. | not_started | 0 | 2 | 0 |  | No entry-signal question copy or component. Existing BetaFeedback form is generic rating/likes/issues, unrelated to 'did the conversation reveal new territory'.
F-013.3 | F-013 | Submit to feedback sheet | Response submits to the central feedback sheet (F-016). | Row appears in feedback sheet within 10s of submit. | not_started | 0 | 4 | 0 |  | No write path tagged 'moment_1' or 'entry_signal'. Existing save-beta-feedback edge function lacks moment discriminator; central sheet (F-016) hasn't been designed.
F-014.1 | F-014 | Inline panel after Forensic Canvas | Inline panel renders below the Forensic Canvas the first time it's viewed. | Panel appears once per user; dismissable. | not_started | 0 | 4 | 0 |  | No inline panel rendered below Canvas. No concept of 'Forensic Canvas' distinct rendering state in the codebase to gate the panel against.
F-014.2 | F-014 | 'What will you do with this?' question with multi-select | Multi-select including 'update existing assets' option (drives the asset-tracking decision gate). | Selections recorded with timestamps; 'update existing assets' specifically tracked. | not_started | 0 | 4 | 0 |  | No multi-select question component or option set. The 'update existing assets' option that drives the asset-tracking decision gate is entirely unbuilt.
F-014.3 | F-014 | Submit to feedback sheet | Response submits to the central feedback sheet. | Row appears in feedback sheet within 10s of submit. | not_started | 0 | 4 | 0 |  | No Moment-2-specific write path. Would need new endpoint or moment_type discriminator on existing endpoint plus F-016 sheet.
F-015.1 | F-015 | Scheduled-send infrastructure | Day-14 emails sent via Resend / Supabase cron; idempotent. | Email sends exactly once 14 days after Forensic Canvas creation. | not_started | 0 | 4 | 0 |  | No scheduled-send infrastructure. pg_cron not enabled, no day-offset queue table, no idempotency keys. Only synchronous Resend call exists (send-framework-email) for a different feature.
F-015.2 | F-015 | Email content + reply parsing | Email asks the question; replies parse into the feedback sheet. | Replies flow into feedback sheet; failures alert Matthew. | not_started | 0 | 4 | 0 |  | No 14-day email template, no inbound reply parsing webhook. Resend inbound parsing not configured.
F-016.1 | F-016 | Central feedback sheet schema | One row per response; columns for moment, user_id, timestamp, payload JSON, parsed key fields. | Schema documented; sheet (or DB view) exists. | not_started | 0 | 4 | 0 |  | Existing beta_feedback table is wide-form (overall_rating, liked_most, improvements, issues) — wrong shape. F-016 spec requires narrow event-row schema (moment, user_id, timestamp, payload JSONB).
F-016.2 | F-016 | Write path from feedback moments | All three feedback moments write to the central sheet. | Test row from each moment appears in the sheet. | not_started | 0 | 4 | 0 |  | No write path from the three moments exists, because the three moments themselves don't exist. The endpoint exists but the contract is wrong for moment-tagged events.
F-017.1 | F-017 | Sentry SDK installed | Sentry installed for both client (Vite) and edge functions. | Errors visible in Sentry dashboard within 1 min of occurrence. | not_started | 0 | 3 | 0 |  | No Sentry (or Rollbar/Bugsnag/LogRocket/Datadog) dep in package.json or lock. ErrorBoundary.tsx:58-61 has only a commented-out placeholder; errors only console.error'd. No edge function error helper.
F-017.2 | F-017 | Daily review cadence documented | Matthew has a documented daily review of Sentry during alpha. | Cadence in tester onboarding doc; first review completed by alpha day 1. | not_started | 0 | 2 | 0 |  | No documented daily Sentry review cadence; precondition (Sentry itself) also absent.
F-017.3 | F-017 | Source maps uploaded on build | Production builds upload source maps to Sentry so stack traces resolve. | Stack traces show original source file/line in Sentry UI. | not_started | 0 | 2 | 0 |  | vite.config.ts sets no sourcemap option (defaults false); no @sentry/vite-plugin; .github/workflows/ does not exist; build script invokes plain vite build with no source-map upload.
F-018.1 | F-018 | Invitation email template | Warm, brief invitation framing 'first 10 people'; sets 7-day window + 30-min debrief expectation. | Template approved by Trevor; sent through Resend. | not_started | 5 | 3 | 0 |  | Resend SDK pattern exists in send-framework-email (different feature). save-beta-tester explicitly disables email ('Resend integration not yet configured'). No invitation template (.html/.tsx/.md), no 'first 10'/'7-day'/'30-min debrief' language anywhere.
F-018.2 | F-018 | One-page Loom + written guide | Short Loom recording + written one-pager covering: what we're testing, the three feedback moments, where to send bugs. | Both assets live and linked from invitation email. | not_started | 10 | 3 | 0 |  | StartHere.tsx has a Vimeo (not Loom) intro video. No one-page written guide. Docs flag training content as missing (BRIEF_ANALYSIS_COMPREHENSIVE.md:288 'No training pages exist'). Not linked from any invitation.
F-018.3 | F-018 | In-app welcome screen | Single-screen welcome acknowledging alpha state; names Trevor + framework. | Welcome screen appears on first login; dismissable; no tutorial. | in_progress | 25 | 2 | 0 |  | BetaWelcome page exists at /beta with 'Beta Testing Program' framing + registration form, but does NOT auto-show on first login, does NOT name Trevor or the framework, is NOT dismissable, gated by localStorage not auth.

## Phase Gate
Phase Gate — readiness gates by launch phase
Mirrors the readiness gates from the Launch Roadmap. gate_status = MET when every mapped feature is complete.
phase | gate_name | gate_requirement | mapped_features | gate_status | notes
Alpha | Layer 1 conversation | All 10 questions function end-to-end. Fallback responses written in Trevor's voice. Canvas sidebar populates in real time. | F-001,F-002 |  | If the entry experience breaks, the tester never reaches anything else.
Alpha | Draft Canvas | Synthesis from Layer 1 produces a coherent canvas with DRAFT badge. | F-003 |  | The Draft-to-Forensic differential is the product's core demonstration of value.
Alpha | Avatar Builder | All sections accept input, persist, and surface AI assistance modes. NB reconcile the 4 sections with the new 5-stage conversational flow ending in The Signature (F-060) — pending sign-off. | F-004,F-005,F-006,F-007,F-009 |  | This is the product per Trevor's Respec.
Alpha | Forensic Canvas | All 28+ fields render, auto-populated from Avatar data. The Decision Trigger™ displayed prominently. | F-008 |  | Trevor flagged Trigger Moment as the single most important field.
Alpha | Manual edit lock | Manually edited fields are flagged. AI never overwrites them silently. | F-011 |  | Trust foundation. Existing PRD constraint.
Alpha | Feedback capture | Three feedback moments wired. Responses route to a single sheet Matthew can monitor. | F-013,F-014,F-015,F-016 |  | No feedback infrastructure = no learning.
Alpha | Error monitoring | Sentry or equivalent active. Errors visible before testers report them. | F-017
Alpha | Tester onboarding doc | One-page Loom + written guide. Sets expectation that this is alpha and frames feedback constructively. | F-018
Alpha | Architectural decision (Lovable vs existing) | Decide explicitly which codebase is canonical for Gen 3. Don't half-port. | F-052 |  | Risk Register: Critical. Two parallel codebases active >1 week triggers escalation.
Beta | Alpha findings synthesised | One-page findings doc. Top 3 product gaps named. | F-016 |  | Synthesis is a Matthew + Trevor activity; tracked via feedback sheet readiness.
Beta | Pay gate functional | Stripe integrated. Both pricing options tested. Post-payment action menu wired. | F-019 |  | Central conversion test of beta.
Beta | Create mode v1 | At minimum: Amazon listing copy + Brand Voice Guide. Forensic canvas drives outputs. | F-020,F-021 |  | Pay-gate previews need real outputs to anchor to.
Beta | Coach mode v1 | Open conversation with full canvas as context. Document upload supported. | F-022 |  | Required for the £29/mo subscription value prop.
Beta | Export | PDF + Word for both Draft and Forensic canvases. | F-023
Beta | Asset Inventory decision | Built or formally deferred based on Alpha % flagging asset-update demand. | F-028 |  | Default is NO. Decision lives in F-028 notes.
Beta | Analytics + funnel tracking | PostHog or Mixpanel events on every funnel step. Cohort analysis possible. | F-024
Beta | Support workflow | Intercom (or email) inbox with documented SLA. | F-025
Beta | Brand Diagnostic integration | Dynamic CTA, score handoff into Layer 1, refreshed visual identity. | F-027
GA | My Brands dashboard | Multi-brand support. Users can manage 2+ brands. Brand switcher works. | F-031
GA | Anonymous-to-authenticated migration | Diagnostic completers without accounts have their data preserved when they sign up. | F-032
GA | Self-serve onboarding | Tooltip-light onboarding tour. No human needed to start. | F-033
GA | Pricing finalised | Pricing tested in beta. Tier structure final. Annual option live. | F-034
GA | Refund policy + ToS + Privacy | Standard SaaS refund (14-day no-questions). Privacy policy. Terms of service. | F-037
GA | Status page | Public uptime page. Incident communication channel. | F-035
GA | Knowledge base | 10–20 articles covering common questions from beta support. | F-036
GA | Pricing page | Pricing page that converts cold traffic. Beta tested. | F-034
GA | Performance metrics tracking | Per-avatar manual entry of ROAS, CTR, CPA, conversion rate, custom metrics. | F-038 |  | OPEN QUESTION: Gen 3 spec does not address; existing V2 PRD scopes it. Treated here as GA P0 pending Matthew sign-off.
Alpha | Trust Gap™ Score lands | Tester sees an aggregated Trust Gap™ Score + widest-gap pillar and feels it's accurate; the bridge explains why building the avatar is next. | F-057,F-059 |  | The #1 thing to validate (Trevor). If the score doesn't resonate, nothing downstream matters.
Alpha | The Signature | Tester produces a one-sentence Signature they recognise as true and had not previously articulated. | F-060 |  | The retention / word-of-mouth moment. Validate alongside the Trust Gap Score, before everything else.
Alpha | The Decision Trigger™ captured | A dedicated screen captures the event that made the customer act today ('why today'). | F-058 |  | Blue-water line #2 vs Pixii — operates at the level of WHEN, not just who.
Alpha | Marketing site live (gated) | ideabrandcoach.com is live; the app is gated, revealing feature sets as they become beta-ready. | F-067 |  | Old consultancy site expires June; Trevor owns this track in Lovable (split-dev).

## Brand Needs
Brand Needs — concrete user needs mapped to features
Anchors the feature inventory to real brand use cases. Each leaf need maps to one or more feature ids. fulfilment_status is derived: MET if all mapped features complete, BLOCKED if any are blocked, otherwise OPEN with count.
need_id | brand | need | mapped_features | fulfilment_status | notes
N-001 | InfinityVault | Create brand strategy doc using the Coach for the 'collector' avatar | F-001,F-004,F-005,F-006,F-007,F-008,F-022,F-023 |  | End-to-end happy path: Layer 1 conversation → Avatar Builder (collector) → Forensic Canvas → Coach refinement → Export. Validates the core product loop with a real brand.
N-002 | InfinityVault | Assess current set of images and videos | F-054 |  | Top-level need under which the gap-identification and emotional-connection needs sit.
N-002.1 | InfinityVault | Identify what's missing in the current image/video set | F-054 |  | Gap analysis on visual assets — requires side-by-side comparison + tagging against the canvas.
N-002.1.1 | InfinityVault | Surface opportunities to improve emotional connection with the customer | F-006,F-007,F-054,F-055 |  | Connects Emotional Journey Mapping (Avatar Builder Sec 3) + Voice of Customer (Sec 4) to the asset gaps surfaced by F-054, with design briefs (F-055) closing the loop into action.

## Risks
Risks — register with current state
risk_id | risk_name | phase_exposed | severity | current_state | trigger_threshold | mitigation_owner | mitigation_status | notes
R-001 | Product doesn't solve enough user problems well enough to earn value | All | Critical | monitoring | At Alpha exit, the Trust Gap™ Score does NOT resonate (testers don't feel the gap is real/accurate) OR The Signature does NOT surprise testers with its accuracy — i.e. fewer than 2 of {P-011 Diagnostic, P-001 Signature/articulation, P-003 strategy doc} verified PARTIAL+ via tester debriefs; OR <50% of testers can articulate one concrete way the canvas changed how they think about their customer; OR fewer than 60% of shipped features map to ≥1 problem. | Matthew | Problems sheet operationalises tracking. Alpha feedback Moments 1 + 2 measure perceived value directly. If signal is low at Alpha midpoint, narrow scope to deepen 1-2 problems rather than adding features. GEN3 (2026-05-25): Trevor's two MVP-critical problems are the Trust Gap™ Score (P-011) and The Signature (P-001) — test those first [Analysis 2026-05-17]. ~2-3yr defensibility window → ship Alpha fast, don't gold-plate; full strategic frame in the Launch Roadmap Overview. | Meta-risk above R-004 (form not conversation) and R-008 (no testimonials). The failure mode where every feature ships on time but the product still doesn't matter to anyone. Operational tool: the Problems sheet — every feature should tag to at least one problem.
R-002 | Alpha testers don't complete the flow | Alpha | High | monitoring | <5 of 8 complete full flow by day 7 | Matthew | Pre-flight QA checklist + daily monitoring + aggressive debrief follow-up planned
R-003 | Trevor's voice doesn't land for younger demographic | Alpha | Medium | monitoring | 3+ testers flag 'sounds old' or 'corporate' | Trevor | Mixed-experience tester pool; tone question in feedback Moment 1
R-004 | Avatar Builder feels like a form not a conversation | Alpha | High | monitoring | Any tester says 'this is just a long form' | Matthew | F-009 AI assistance wired before alpha; F-010 progressive disclosure tested; question phrasing reviewed by Trevor | Kills Trevor's core thesis if it materialises. Specific symptom of R-001.
R-005 | Pay gate conversion too low | Beta | High | monitoring | <8% Draft viewers convert at 4-week mark | Matthew | Pay-gate previews use actual canvas data; pricing differentiated by job not features; A/B test framing
R-006 | Refund rate is high | Beta | Medium | monitoring | >10% refund rate | Matthew | Forensic canvas over-delivers vs pay-gate promise; 14-day refund window
R-007 | Asset tracking sucks Beta scope dry | Beta | Medium | monitoring | Builder spending >2 weeks on asset tracking in beta phase | Matthew | Decision gate at end of Alpha with hard threshold; v1 only if shipped
R-008 | ROI testimonials don't materialise | Beta | High | monitoring | <3 testimonials by week 4 of beta | Matthew | Testimonial harvest sequence baked in from day 1; results-focused user selection | Kills the marketing engine if it materialises. Downstream symptom of R-001.
R-009 | GA acquisition CAC too high | GA | High | monitoring | Paid CAC payback >4 months after 30 days of spend | Matthew | Build organic foundation in beta; don't scale paid until CAC payback known
R-010 | Retention below unit economics floor | GA | Critical | monitoring | <50% retention at week 4 | Matthew | Retention motion built before GA; quarterly Voice of Customer refresh designed in
R-011 | TikTok algorithm de-prioritises long-form B2B content | Post-GA | Medium | monitoring | Organic engagement <2% after 30 days of content | Matthew | Organic test before paid; cap spend at £500/wk in test phase
R-012 | Trevor's bandwidth limits content production | All | Medium | monitoring | Trevor unavailable >2 weeks consecutively | Matthew | Batch recording; async content review; develop a second voice as backup
R-013 | Lovable.dev vs existing codebase architectural collision | Alpha | Low | resolved | Two parallel codebases active >1 week | Matthew | RESOLVED — split-dev decision recorded (F-052) | RESOLVED 2026-04-23 [F 140678453]: split dev — Matthew builds backend in Claude Code, Trevor builds the marketing site in Lovable; beta stays on Lovable; custom server deferred until traction. Downgraded Critical→Low.
R-014 | Competitor launches similar tool (StoryBrand framework / Pixii execution) | Beta | Medium | monitoring | Competitor announcement or feature ship | Matthew | Speed; first-mover positioning on the Forensic Avatar Builder; lean into the Voice of Customer differentiator | Two distinct vectors: StoryBrand (framework competitor) and Pixii (execution/image tool with a strategy layer). GEN3 (2026-05-25): 5 blue-water lines vs Pixii — (1) evidence vs inference, (2) The Decision Trigger™, (3) Trust Gap™ Diagnostic, (4) Coach as a live briefing not a one-shot PDF, (5) framework ownership. Position upstream of Pixii ('build the brief in IDEA, execute anywhere'), not as a competitor [Analysis 2026-05-17].
R-015 | Trevor changes framework spec mid-build | All | High | monitoring | Any framework field change requested post-Alpha launch | Matthew | Lock the v2 Brief; require written sign-off on changes; version-tag the build
R-016 | Single-developer velocity / availability | All | High | monitoring | No app progress in any 2-week window; another deadline slips | Matthew | Lock a small hard Alpha scope; timebox; Trevor owns the marketing-site track in parallel | GEN3 (2026-05-25): the dominant live risk. Matthew is repeatedly pulled to higher-paying work; the May-1 beta target was already missed and the project is in a re-planning holding pattern [WA 2026-01-23,02-20,04-18,05-13..16].
R-017 | Knowledge-storage architecture undecided | Alpha | Medium | monitoring | KB work blocks F-049 / coach grounding | Matthew | Pick one for Alpha; defer 'offer both'; spike before committing | Knowledge-graph vs spreadsheet vs Obsidian; 'where does the KB sit — Supabase?' [WA 2026-04-24,05-19].
R-018 | Titan conflict-of-interest | Beta | Medium | monitoring | Titan declines or restricts promotion | Matthew | Resolve with Dan/Titan before relying on that channel; line up alternative beta sources | Athena said Trevor 'can't promote this to members', yet the beta targets the Titan AI work party [F 140678453 @31:30].
R-019 | ProductPinion may not support landing-page A/B | Alpha | Low | monitoring | Capability unconfirmed at site launch | Trevor | Trevor confirms with ProductPinion contact; else build split-test scaffolding (F-066) | ProductPinion may only support listing A/B, not landing-page split testing [F 140678453 @34:09].

## Change Log
Change Log — append-only
date | who | what_changed | reason
2025-11-22 | Matthew ↔ Trevor (WhatsApp) | Core thesis: get brand owners to switch from ChatGPT to the app (work gets lost in threads) | Area(s): conversation ¦ Source: WhatsApp 2025-11-22.
2025-11-27 | Matthew ↔ Trevor (WhatsApp) | Pre-fill fields from users' existing brand docs (initially via a NotebookLM template) rather than re-typing | Area(s): avatar_builder, infrastructure ¦ Source: WhatsApp 2025-11-27.
2025-12-15 | Matthew ↔ Trevor (WhatsApp) | Data model → per-user AND per-brand separation (triggered by the coach conflating two brands) | Area(s): infrastructure, accounts, coach_mode ¦ Source: WhatsApp 2025-12-15.
2025-12-19 | Matthew ↔ Trevor (WhatsApp) | Brand Canvas = central synthesis layer pulling from all modules | Area(s): canvas ¦ Source: WhatsApp 2025-12-19.
2025-12-25 | Matthew ↔ Trevor (WhatsApp) | System Knowledge Base (vector store) seeded with Trevor's book; RAG-grounded | Area(s): infrastructure, coach_mode ¦ Source: WhatsApp 2025-12-25.
2026-01-16 | Matthew ↔ Trevor (WhatsApp) | Beta-Ready Scope formalized ($1000/Phase 1): Insight Module + Approval Gate + single unified strategy doc; billing deferred | Area(s): multi ¦ Source: WhatsApp 2026-01-16.
2026-01-26 | Matthew ↔ Trevor (WhatsApp) | Cut non-functional pages — every page must produce an output | Area(s): design_system ¦ Source: WhatsApp 2026-01-26.
2026-02-21 | Matthew ↔ Trevor (WhatsApp) | Trevor freezes scope: 'no additional features, speed is priority' | Area(s): all ¦ Source: WhatsApp 2026-02-21.
2026-03-01 | Matthew ↔ Trevor (WhatsApp) | Positioning: authority on branding/avatar/messaging + results tracking; don't compete on content generation | Area(s): strategy ¦ Source: WhatsApp 2026-03-01.
2026-03-18 | Matthew ↔ Trevor (WhatsApp) | 3-tier commercial model (App / Brand Community / 1:1 Consultancy); Agentic Commerce / AVM module idea | Area(s): create_mode ¦ Source: WhatsApp 2026-03-18.
2026-04-06 | Matthew ↔ Trevor (WhatsApp) | Migrate AI backend OpenAI → Anthropic/Claude (cost + maintainability) | Area(s): infrastructure ¦ Source: WhatsApp 2026-04-06.
2026-04-12 | Matthew ↔ Trevor (WhatsApp) | Gen 3 respec: conversation-first; Avatar Builder = core; three modes Canvas/Create/Coach | Area(s): all ¦ Source: WhatsApp 2026-04-12.
2026-04-23 | Gen 3 meeting (Fathom 140678453, 140691318) | Split dev (Matthew backend in Claude Code / Trevor marketing in Lovable); beta on Lovable; ideabrandcoach.com | Area(s): infrastructure ¦ Source: Fathom 140678453 + 140691318. Resolves F-052 / R-013.
2026-05-02 | Matthew ↔ Trevor (WhatsApp) | Gen 3 doc set delivered (8 docs incl. Avatar 2.0 field spec + Decision Trigger™) | Area(s): all ¦ Source: WhatsApp 2026-05-02.
2026-05-06 | Gen 3 meeting (Fathom 144128256) | Gen 3 mockup: Trust Gap™ Score, Decision Trigger™ screen, Customer Insight Engine™, bridge screen, freemium, locked-but-visible fields | Area(s): conversation, avatar_builder, canvas, pay_gate ¦ Source: Fathom 144128256. Basis for F-057..F-064.
2026-05-13 | Matthew (via Claude Code) | Initial workbook created | Operational counterpart to Launch Roadmap; seeded from Gen 3 brief, V2 PRD, and Launch Roadmap workbook.
2026-05-13 | Matthew (via Claude Code) | Added F-053..F-056 + Brand Needs sheet | Captured multi-angle, image comparison, design brief, and (post-GA) image generation features. Added Brand Needs sheet seeded with InfinityVault as the first validation case.
2026-05-16 | Matthew ↔ Trevor (WhatsApp) | Three-phase launch (Alpha→Beta→GA) formalized; Launch Roadmap + Feature Status Tracker created; placeholder 6-week target (to tighten) | Area(s): all ¦ Source: WhatsApp 2026-05-16.
2026-05-16 | Matthew (via Claude Code) | Corrected status for brand strategy doc + PDF export; added Problems sheet | F-008 was wrongly marked not_started — corrected to in_review 80% based on shipped generate-brand-strategy-document. F-023 corrected to in_progress 65% (PDF + Markdown shipped, Word still missing). Added Problems sheet with the 10 problems we solve mapped to features; added problems_addressed column on Features.
2026-05-16 | Matthew (via Claude Code) | Full sub-feature audit against the codebase (6 parallel agents) | Audited all 64 sub-features against actual code on main. Major findings: (a) F-008 dropped 80→39% — the strategy doc ships but the Forensic *tier* concept and Trigger Moment callout don't exist in code; (b) F-002.2 + F-012.2 reduced from 100% — quality badges use value heuristics, not extractor confidence; (c) F-009 dropped 30→19% — only ONE AI mode is independently invocable, not four; (d) F-011.1 reduced from 100→70% — code uses field_source + separate is_locked, not a manuallyEdited boolean; (e) all of F-013/F-014/F-015/F-016 confirmed 0 — no three-moment infra exists; existing BetaFeedback is a separate older system that won't compose; (f) F-017 confirmed 0 — no Sentry installed. Per-sub-feature notes updated with file:line evidence; parent features rolled up to averages.
2026-05-17 | Trevor (strategic analysis) | Strategic analysis: 10 problems; MVP must validate Trust Gap™ + The Signature first; no image generation; 'blue water' vs Pixii | Area(s): strategy ¦ Source: IDEA App 3 v3 Claude Analysis 17 May 2026.
2026-05-25 | Matthew (via Claude Code) | Folded in Context Delta 2026-05-25 + v2 Launch Roadmap (WhatsApp + Gen 3 Fathom transcripts) | Added F-057..F-067; freemium reframe (F-019); F-052/R-013 resolved (split dev, 4/23); F-056 → deliberate non-goal; added R-016..R-019; reconciled Avatar Builder 4→5 stages (flagged); added P-011/P-012; sharpened R-001 to the Trust Gap + Signature validation bar; named StoryBrand + Pixii in R-014; added Alpha gates for Trust Gap / Signature / Decision Trigger; seeded the dated decision trail.