## Overview
IDEA Brand Coach — Refactor & Architecture Build Plan (v2-and-beyond)
Version / Date | v1 — 2026-05-26. Author: BMad Master. Scope: v2 experience + shared edge-function backend.
Objective | Make v2 a maintainable, viable app that gives users the best UX solving their problem, where technical errors are identified, logged, and fixed FAST — sequenced to serve the Alpha->Beta->GA roadmap.
STEERING (Matthew, 2026-05-26) | 1) v2 is canonical. 2) v1 (/v1/* legacy namespace) stays in place — DO NOT DELETE ANYTHING YET. 3) Do NOT refactor old code unless it supports current or planned functionality. This plan touches v2 + shared backend ONLY.
Governing constraint | Refactor spend <=20-30% of any 20h sprint (<=4-6h), unless an item is massive-impact (justified inline). Current ship week (Sprint v3) is REFACTOR-FROZEN. Work below schedules into the next sprints' buffer / Always-On.
Method / honesty | Every finding re-verified against real code (grep + file reads), not graph inference alone. Routing confirmed v1 is fully namespaced under /v1/* with VersionGate -> /v2/coach as the live entry. Unverified items marked AMBIGUOUS.
The 4 product primitives | Nearly every roadmap feature reduces to: (1) conversation -> structured fields; (2) local-first edit-aware persistence; (3) Trevor-voiced LLM artifact; (4) feedback moment. The target abstractions ARE these — built once, in v2/shared.
v1 disposition (summary) | KEEP (load-bearing now): /free-diagnostic, /beta*, /v1/canvas. FREEZE: the rest of /v1/* — leave untouched, no refactor, no delete. FUTURE: decommission is a real LOC win but DEFERRED until v2 supersedes the kept surfaces. See 'V1 Disposition' tab.
Headline recommendation | Spend the first reclaimed budget on the OBSERVABILITY SEAM (RF-01/RF-02). It is simultaneously an Alpha roadmap GATE, the user's #1 goal, and risk-reduction for 12+ shared LLM edge functions. Treat as the massive-impact exception.
How to use | 1 Overview ¦ 2 Target Abstractions ¦ 3 Refactor Backlog (priority-ordered; update Status) ¦ 4 Observability Plan ¦ 5 Sequencing (<=30%/sprint) ¦ 6 V1 Disposition ¦ 7 Out of Scope.

## Target Abstractions
# | Abstraction (v2/shared) | Verdict | Current state (verified) | What to build / change | Rationale & roadmap leverage
1 | Single Field-Extraction pipeline (v2) | ACCEPT | Within v2/shared the conversation->fields logic appears in 3 places: v2/components/EnhancedChatInterface.tsx (extractFieldsFromContent), inline regex in V2ChatPanel, and hooks/useFieldExtraction.ts (474L) used by v2. (v1 utils/fieldExtractionParser.ts is LEFT ALONE.) | One canonical v2 extractor, schema-driven off CHAPTER_FIELDS_MAP; v2 callers delegate to it. Do not touch v1's copy. | Core v2 flow. Unblocks Avatar 2.0 (F-004..007), Review Lab (F-063), Decision Trigger (F-058).
2 | One v2 Field Repository (edit-aware) | ACCEPT | v2 sync hooks (useAvatarFieldSync, useFieldDatabaseSync, useSimpleFieldSync, useFieldSync) sit over the knowledge-base spine (knowledge-repository.ts 344L + supabase-sync-service.ts 429L, already implements I*Repository/ISyncService w/ retry+backoff). v1 lib/sync/FieldSyncService.ts + services/field/FieldValueStorageService.ts serve v1 only. | Converge the v2 field hooks onto the knowledge-base repository; manual-edit lock in EXACTLY one place. Freeze v1 sync code in place. | Trust foundation. Alpha gate + QA require 'manual edits never silently overwritten'. Highest correctness risk.
3 | Typed LLM edge-function client (shared) | ACCEPT | 23 edge functions, ~12 LLM-calling (brand-ai-assistant, reveal-signature, diagnostic-interpretation, brand-copy-generator, ai-insight-guidance, contextual-help, buyer-intent-analyzer, generate-brand-strategy-section...). No shared typed client; quota errors hide in HTTP-200 SSE bodies (memory: feedback_sse_stream_capture). Backend is shared by v1 AND v2. | One typed client: invoke + SSE parse + quota/error-envelope detection + retry/timeout. All current + future generators are instances. | The Create-mode generator base (F-020/021/055/063). Closes the riskiest observability gap on the most failure-prone surface.
4 | Result<T> propagated + reportError sink | ACCEPT (cheap) | ErrorBoundary EXISTS (components/ErrorBoundary.tsx 122L; shared). Result<T> EXISTS in v2 (v2/shared/types, domain, lib/knowledge-base/interfaces). NO reportError/captureException/Sentry anywhere. | Add one reportError() sink (console+overlay now, Sentry-ready interface). Wire ErrorBoundary to it. Propagate Result<T> across v2 boundaries. | Satisfies Alpha 'error monitoring' gate cheaply. Identify->log->fix loop. Most infra already seeded in v2 — wiring, not building.
5 | Enforce DI data access (v2/shared) | ACCEPT (enforce, don't build) | DI spine holds: ServiceProvider + interface-typed services. Real leaks in scope: ~2 files in hooks/v2 import the raw client. (v1 chat-component leaks are LEFT ALONE per steering.) | Retire the hooks/v2 raw-client imports onto useServices()/interfaces. Add an eslint guard scoped to v2. | Decouples the supabase god-node (57 edges) for v2; enables clean mocking. Incremental / boy-scout.
6 | FeedbackMoment primitive (shared) | ACCEPT | Write path exists (BetaFeedbackWidget.tsx -> feedback_events). Roadmap defines 3 moments used across ALL phases; this week ships Moment 1. | Extract <FeedbackMoment moment={1¦2¦3}> writing feedback_events with consistent payload + skip-as-data behaviour. Used by beta flow + v2. | Moments 1/2/3 recur Alpha->Beta->GA (Feedback Loop sheet). Build once; Branch-A next sprint adds Moment 2.
7 | v1-vs-v2 canonical | RESOLVED -> v2 | Routing: whole v1 surface namespaced /v1/* as 'legacy support'; VersionGate -> /v2/coach is the live entry. useBrandCoachV2State is mid-extraction into useChatOrchestration/useFieldOrchestration/useBrandCoachUI (worst-of-both right now). | No v1 deletion now. In-scope action is COMPLETING the v2 orchestration extraction (RF-07 below) — that is current live functionality. | Resolves the risk-register 'two warm codebases' item by direction (v2 wins) without touching v1.

## Refactor Backlog
ID | Priority | Refactor (v2/shared) | Why | Key files | Effort (h) | Risk | Blast radius | Leverage | Roadmap F-IDs | Recommended sprint | Allocation | Status
RF-01 | P0 | Typed LLM edge-fn client (abstraction #3) | 12+ shared LLM edge fns each hand-roll invoke/SSE/error handling; quota errors hide in HTTP-200 bodies -> silent failures users hit. | NEW src/services/llm/EdgeFunctionClient.ts; supabase/functions/_shared; wraps brand-ai-assistant, reveal-signature, diagnostic-interpretation +9 | 3-4 (thin)/6-8 (full) | Med | High (12+ fns) | High | F-020/021/055/063 | Next sprint (06-01) | Thin slice 3-4h | not_started
RF-02 | P0 | reportError sink + Result<T> propagation (abstraction #4) | No error reporting sink; Alpha gate REQUIRES 'see errors before testers report them'. ErrorBoundary + Result<T>(v2) already exist. | src/components/ErrorBoundary.tsx; NEW src/lib/observability/reportError.ts; src/v2/shared/types/index.ts | 2-3 | Low | Med (v2) | High | Alpha error GATE | Next sprint (06-01) | 2-3h | not_started
RF-03 | P1 | Converge v2 Field Repository + single edit-lock (abstraction #2) | v2 field-sync hooks duplicate persistence over the knowledge-base spine; manual-edit lock (the trust foundation) is spread out. | src/hooks/{useAvatarFieldSync,useFieldDatabaseSync,useSimpleFieldSync,useFieldSync}.ts -> src/lib/knowledge-base/* (KEEP target) | 6-8 (split 2 sprints) | HIGH | High (v2 fields) | High | Alpha 'no overwrite' GATE | Sprints +2 / +3 | 4h then 3h | not_started
RF-04 | P1 | Finish useBrandCoachV2State extraction (abstraction #7 action) | Live /v2/coach state hook is mid-extraction into 3 orchestrators that duplicate slices = worst of both. This is CURRENT functionality. | src/hooks/v2/{useBrandCoachV2State,useChatOrchestration,useFieldOrchestration,useBrandCoachUI}.ts | 3-5 | Med | High (live coach) | High | Coach mode (F-022) | Sprint +2 | 3-5h | not_started
RF-05 | P2 | Unify v2 Field-Extraction pipeline (abstraction #1) | 3 reimplementations of conversation->fields inside v2 drift apart; every extracting feature multiplies divergence. | src/v2/components/EnhancedChatInterface.tsx; V2ChatPanel inline regex; src/hooks/useFieldExtraction.ts (v1 copy left alone) | 4-6 | Med | High | High | F-004..007, F-058, F-063 | Sprint +3 | 4-6h | not_started
RF-06 | P2 | Extract FeedbackMoment primitive (abstraction #6) | Moments 1/2/3 recur across all phases; building each inline duplicates write/skip/payload logic. | src/components/BetaFeedbackWidget.tsx; src/pages/BetaFeedback.tsx; NEW src/components/feedback/FeedbackMoment.tsx | 2-3 | Low | Med | Med | Feedback Moments 1/2/3 | Branch-A next sprint | 2-3h | not_started
RF-07 | P3 | Enforce DI data access in v2 (abstraction #5) | ~2 hooks/v2 files leak the raw supabase client, coupling v2 UI to the data plane and blocking mocking. | src/hooks/v2/* (raw client imports); eslint no-restricted-imports guard scoped to v2 (v1 excluded) | 1-2 (incremental) | Low | Low (v2) | Med | Testability | Boy-scout / Always-On | ~0.5h per touch | not_started
RF-08 | P4 | Collapse v2 cosmetic duplicates | Parallel implementations of the same v2 UX: hygiene only, but inflate surface area and confuse contributors. | v2: MilestoneCelebration vs MilestoneOverlay; GhostTextChatInput vs GhostTextFieldWrapper; useRejectionMessages vs useRejectionToChat; BrandsList vs SimpleBrandPanel; shared sonner vs toast/toaster | 3-4 (spread) | Low | Low | Low | (hygiene) | Always-On / buffer | opportunistic | not_started
TOTAL (v2/shared) |  | ~24-35h across 3+ sprints @ <=6h/sprint. v1 NOT included (frozen). RF-01/02 first.

## Observability Plan
Observability Plan — identify -> log -> fix, fast (v2 + shared backend)
Goal | A technical error is (a) IDENTIFIED before a tester reports it, (b) LOGGED with reproduce-able context, (c) FIXED fast. This is the Alpha 'Error monitoring' gate and the user's #1 objective.
Layer 1 — Edge-fn envelope | An LLM edge fn can return HTTP 200 while the SSE body carries a billing/quota/length error (memory). RF-01: the typed client inspects the stream, classifies (quota¦rate-limit¦content¦network¦unknown), returns a typed error not a silent blank.
Layer 2 — Result<T> boundaries | Every v2 service/edge call returns Result<T> (already the v2 convention). UI branches ok/err and renders a real error state instead of a blank/partial screen. RF-02 propagates it across v2 call sites.
Layer 3 — reportError sink | Single src/lib/observability/reportError.ts(error, context): structured console + a ring buffer in a dev overlay. Sentry-ready interface (swap transport, not call sites). RF-02.
Layer 4 — ErrorBoundary wiring | Existing ErrorBoundary calls reportError and shows a recoverable fallback. Add route-level boundaries around the diagnostic, signature, and /v2/coach flows so one feature crash never blanks the app.
Layer 5 — Supabase reachability | Free-tier auto-pause -> NXDOMAIN/timeouts/INACTIVE (memory: project_supabase_pauses). Add a boot health ping + a user-facing 'service paused' banner instead of a silent failure.
Sentry-ready seam | Do NOT install Sentry this cycle (T10/F-017 deferred). Build the seam so adopting Sentry at Beta is a one-file transport swap. Console + dev overlay suffices for the alpha friend-tester cohort.
Definition of done | Walk diagnostic->signature->feedback with Supabase PAUSED and with a forced edge-fn quota error. Both yield a clear recoverable error AND reportError captures cause + route + payload shape.

## Sequencing
Sprint / window | Mode | Refactor budget (<=30%) | Scheduled items | Dependency / rationale
Sprint v3 — wk 2026-05-25 | SHIP (frozen) | 0h (frozen) | (none) | Ship-week: Trust Gap + Signature on critical path T8->T3->T4->T5->T9. Refactoring here = scope creep per the plan.
Sprint +1 — wk 2026-06-01 | Conditional A/B/C | <=6h (30%) | RF-02 (2-3h) + RF-01 thin slice (3-4h) | Observability first: it's an Alpha gate AND helps Branch-B diagnose WHY a v2 output failed. Confirm v2-canonical direction in planning (no v1 action).
Sprint +2 — wk 2026-06-08 | Build | <=6h (30%) | RF-04 finish v2 coach extraction (3-5h) + RF-07 incremental (1h) | Stabilise live /v2/coach before deeper field work. RF-04 is current functionality, so high value within budget.
Sprint +3 — wk 2026-06-15 | Build | <=6h (30%) | RF-03 pt1 (4h) + RF-06 (2h) | Field Repository convergence depends on the observability seam (debuggable migration). FeedbackMoment slots into Branch-A feature work.
Sprint +4 — wk 2026-06-22 | Build | <=6h (30%) | RF-03 pt2 (3h) + RF-05 (3h) | Finish repository convergence before unifying extraction (extraction writes through the repo).
Always-On / buffer | Continuous | opportunistic | RF-07 DI touches; RF-08 cosmetic dupes | Hygiene with no gate dependency. Touch when already in the file (boy-scout), never as standalone sprint cost.
Massive-impact exception | Note | — | RF-01 + RF-02 (~5-7h) | Exceed the 'cheap' bar but justified: simultaneously an Alpha GATE, the #1 goal, and risk-reduction for 12+ edge fns. If Sprint +1 is Branch-B, they are arguably ON the critical path, not refactor overhead.

## V1 Disposition
V1 Disposition — NO ACTION NOW (no delete, no refactor)
Per steering: v1 stays in place. This tab records the disposition so a future decommission is a deliberate, evidence-backed decision — NOT something done now. Classification by route reachability from the live (non-/v1) flow.
v1 surface | Disposition | Evidence / reachability | Why | Future action (deferred)
/free-diagnostic + DiagnosticResults | KEEP | Live flow step 3-5 (sprint User Flow Contract); not under VersionGate redirect. | Feeds the Trust Gap Score; current + planned functionality depends on it. | None. Eventually re-skin under v2 shell.
/beta, /beta-journey, /beta-feedback | KEEP | Live alpha onboarding + Moment-1 feedback (T5/T6/T7 this sprint). | Active tester funnel; FeedbackMoment primitive (RF-06) builds on it. | None. Fold into v2 onboarding at Beta.
/v1/canvas (Brand Canvas) | KEEP | Sprint Fri-QA: 'Existing /brand-canvas still works — no regressions.' | Still referenced as a working surface; Signature->Canvas bridge is planned (Branch-A T-A2). | Re-implement as v2 Canvas when the bridge ships; then retire v1 canvas.
/v1/idea/* (insight, distinctive, empathy, authenticity, consultant) | FREEZE | Reachable only via /v1/* legacy redirects; not linked from VersionGate or /v2/coach. | Superseded by the v2 coach experience. Not current/planned functionality. | Decommission candidate AFTER v2 coach fully covers the IDEA modules.
/v1/start-here, /v1/journey, /v1/dashboard | FREEZE | Legacy entry/nav; live entry is VersionGate -> /v2/coach. | Replaced by v2 entry. No current dependency. | Decommission candidate.
/v1/avatar, /v1/brand-diagnostic, /v1/idea-diagnostic | FREEZE | Legacy /v1/* only. | Avatar 2.0 ships in v2; v1 avatar/diagnostics superseded. | Decommission candidate.
/v1/copy-generator, /v1/research-learning, /v1/conversations | FREEZE | Legacy /v1/* only. | Create-mode + research re-built in v2/Beta scope. | Decommission candidate.
v1-only services/hooks (FieldSyncService, FieldValueStorageService, fieldExtractionParser) | FREEZE | Imported by v1 surfaces; not the v2 knowledge-base spine. | Leaving them avoids touching old code that doesn't serve current objectives. | Remove with their v1 surfaces during decommission.
Decommission trigger (future) |  | Only when v2 fully covers the KEEP surfaces (diagnostic, beta, canvas) AND analytics show /v1/* traffic ~0. Then do a measured, test-guarded removal — its own task, never inside a ship week.

## Out of Scope
Item | Why out of scope (now) | Revisit when
Deleting ANY v1 code | Explicit steering: no deletion yet. v1 stays in place; disposition recorded on the V1 Disposition tab. | Future decommission task once v2 supersedes the KEEP surfaces.
Refactoring v1 internals | Steering: do not touch old code unless it serves current/planned functionality. The KEEP surfaces work as-is. | Only if a KEEP surface (diagnostic/beta/canvas) needs a change for a planned feature.
Full Sentry / APM install (F-017) | Console + dev overlay + reportError seam is enough for the alpha cohort. Installing now is cost without payoff. | Beta (paying users) — swap the reportError transport.
Rewriting the 23 edge functions | RF-01 wraps them behind one client; rewriting internals is unnecessary and high-risk. | Only if a specific fn proves unreliable in alpha.
Test-coverage backfill | Separate from structural refactor. Add characterization tests AROUND each refactor as you make it. | Per-refactor, inline.
Design-system / shadcn cleanup | cn()/Button/Card god-nodes are unavoidable shared primitives. Toast dedupe is the only real item (RF-08). | Opportunistic only.
Performance optimization | No evidence of a perf problem in the graph or transcripts. Premature. | When a measured perf issue appears.